## 갑지 (hidden)
제 R241030-01H호
見 積 書
작성일자 : 2025-08-20
| 통영에코파워 |  |  | 귀중
아래와 같이 견적합니다
프로젝트 :통영에코파워 SCR 성능개선 (Direct Injection Type)
| 合計金額 : |  | #REF!
#REF!
| 지불조건 : |  | 추후협의
| No. | 名 稱 DESCRIPTION |  | 規 格 Specification | 數量 Q'ty | 單位 Unit | 單價 Price | 金 額 Amount
■ 통영에코파워 SCR 환경설비 개선 제안 (Direct Injection System)
|  | 직접분사 설비 X HRSG 2기 |  |  | 1 | LOT | #REF! | #REF!
|  | TOTAL PRICE |  | VAT 별도 |  |  | 백만단위절사 | #REF! |  | 1330000000
대 표 이 사 : 김 종 섭 (직인 생략)
ECOPRO Co., Ld.
충청북도 청주시 청원구 오창읍 송대리 311-1
TEL : +82 43) 240-7700 FAX : +82 43)241-7771
http://www.ecopro.co.kr
※ REMARK
1) 견적 외 사항 제외
2) 납기 : 추후 협의
3) 유효기간 : 견적일로부터 1개월
4) 담당자 : 플랜트기술1팀 한태권 수석
010-6754-0826

## 공사원가내역서 (hidden)
프로젝트 :통영에코파워 SCR 성능개선 (Direct Injection Type)
번호 | 구 분 | 항 목 | 수 량 | 단위 | 단 가 | 금 액 | 비 고
1. | 직접공사비
1) | 재료비 | 재료비 (완제품가액 포함) | 1 | Lot | 522385000 | 522385000
소 계 | [5 empty] | 522385000
2) | 노무비 | 직접노무비 | 1 | Lot | 93000000 | 93000000
소 계 | [5 empty] | 93000000
3) | 경비 | 경비 | 1 | Lot | 316255000 | 316255000
소 계 | [5 empty] | 316255000
직 접 공 사 비 계 (1) | [5 empty] | 931640000
2. | 간접공사비
1) | 간접노무비 | 직접노무비의 | 16.5 | % |  | 15345000
2) | 산업재해보상보험료 | 노무비의 | 3.56 | % |  | 3857082
3) | 고용보험료 | 노무비의 | 1.01 | % |  | 1094284.5
4) | 국민건강보험료 | 직접노무비의 | 3.545 | % |  | 3296850
5) | 국민연금보험료 | 직접노무비의 | 4.5 | % |  | 4185000
6) | 노인장기요양보험료 | 건강보험료의 | 12.95 | % |  | 426942.075
7) | 산업안전보건관리비 | (재료비+직접노무비+완제품가액)×요율 + 기초액과 ((재료비+직접노무비)×요율 + 기초액)×1.2 중 작은 금액 | 2.53 | % |  | 18869240.5 | 3300
8) | 환경보전비 | 직접공사비의 | 0.4 | % |  | 3726560
9) | 퇴직공제부금비 | 직접노무비의 | 0 | % |  | 0
10) | 하도급대금지급보증 수수료 | 직접공사비의 | 0.081 | % |  | 754628.4
11) | 건설기계대여대금 지급보증서 발급비 | 직접공사비의 | 0.16 | % |  | 1490624
12) | 기타경비 | (재료비 + 노무비)의 | 5.2 | % |  | 32797960
13) | 공사이행보증수수료 | 선급금보증, 계약이행보증, 하자이행보증 | - | - |  | #REF!
간 접 공 사 비 계 (2) | [5 empty] | #REF!
프로젝트 :통영에코파워 SCR 성능개선 (Direct Injection Type) 번호: 순 공 사 원 가 (1+2); 프로젝트 :통영에코파워 SCR 성능개선 (Direct Injection Type) 금 액: #REF! | #REF!
3. | 일반관리비 | (재료비 + 노무비 + 경비)의 | 8 | % |  | 74531200
4. | 이윤 | (순공사원가 + 일반관리비)의 | 0 | % |  | #REF!
5. | 완제품 가액
총 공 사 금 액 (1+2+3+4) | [5 empty] | #REF!
공 사 원 가 내 역 서
Note on D15: 요율 변경 가능 (조달청 분석요율이며, 법정 요율은 아님)
Note on G24: '참고)하도급대금지급보증 수수료' 시트에서 계산된 금액과 비교하여 더 큰 금액으로 반영
Note on D28: 요율 변경 가능 (조달청 분석요율이며, 법정 요율은 아님)
Note on G29: '참고)공사이행보증 수수료율' 시트에서 계산된 금액을 반영
Note on D32: 요율 변경 가능 (조달청 분석요율이며, 법정 요율은 아님)

## 을지 (hidden)
[10 empty] | 제 R200420-01Y호 | [5 empty] | 제 R200420-01Y호
( 단위 : 원)
품 명 | 규 격 | 수량 | 단위 | 합 계 |  | 재료비 |  | 노무비 |  | 경 비 |  | 비 고 | 재료비 |  | 노무비 | 경 비
|  |  |  | 단가 | 금액 | 단가 | 금액 | 단가 | 금액 | 단가 | 금액 |  | 단가 |  | 단가 | 단가
■ 통영에코파워 SCR 환경설비 개선 제안 (Direct Injection System)
1. Urea Storage & Supply System |  | 1 | LOT | 0 | 0 |  | 0 |  | 0 |  | 0 | 기존 설비 사용
2. SCR and Auxiliary System |  | 1 | LOT | 0 | 0 |  | 0 |  | 0 |  | 0 | 기존 설비 사용
3. Urea Injection System |  | 1 | LOT | 282000000 | 282000000 |  | 282000000 |  | 0 |  | 0
4. Electric & Instrument |  | 1 | LOT | 60000000 | 60000000 |  | 60000000 |  | 0 |  | 0
5. Bulk Material |  | 1 | LOT | 69000000 | 69000000 |  | 69000000 |  | 0 |  | 0
6. Miscellaneous |  | 1 | LOT | 4000000 | 4000000 |  | 4000000 |  | 0 |  | 0
7. Emgineering Service |  | 1 | LOT | 95000000 | 95000000 |  | 0 |  | 0 |  | 95000000
8. Installation Fee |  | 1 | LOT |  | 421640000 |  | 107385000 |  | 93000000 |  | 221255000
총 공 사 비 합 계 |  |  |  |  | 931640000 |  | 522385000 |  | 93000000 |  | 316255000 |  | 931640000
1. Urea Storage & Supply System | [11 empty] | 기존 설비 사용
1-1. Urea Storage Tank Unit
1) Urea Storage Tank |  | 1 | SET | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2) Electric Heater |  | 1 | SET | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3) Platform with Stair for Ammonia Storage Area |  | 2 | ton | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
소 계 |  |  |  |  | 0 |  | 0 |  | 0 |  | 0
합 계 |  |  |  |  | 0 |  | 0 |  | 0 |  | 0
2. SCR and Auxiliary System
2-1. Catalyst
1) SCR Catalyst with Module |  | 1 | LOT | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 기존 설비 사용
소 계 |  |  |  |  | 0 |  | 0 |  | 0 |  | 0
2-2. Catalyst Support Structure |  | 1 | Ton | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 기존 설비 사용
소 계 |  |  |  |  | 0 |  | 0 |  | 0 |  | 0
2-3. Monorail Hoist |  | 1 | LOT | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 기존 설비 사용
소 계 |  |  |  |  | 0 |  | 0 |  | 0 |  | 0
합 계 |  |  |  |  | 0 |  | 0 |  | 0 |  | 0
3. Urea Injection System
3-1. Circulation Module Skid |  | 1 | LOT
1) Urea Supply Pump |  | 3 | SET | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 기존 설비 사용
2) Skid Frame 제작 |  | 1 | LOT | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 기존 설비 사용
소 계 |  |  |  |  | 0 |  | 0 |  | 0 |  | 0
3-2. Metering Module Skid
1) Metering Module Skid | Container 구성 | 2 | LOT | 36000000 | 72000000 | 36000000 | 72000000 | 0 | 0 | 0 | 0
- Pneumatic On-off Ball Valve | 40A | 2 | EA
- Flow Transmitter | 15A, Magnetic | 2 | EA
- Flow Control Valve | 15A, Magnetic | 2 | EA
- Pneumatic On/off Valve |  | 5 | EA
- Diaphragm Pressure Gauge |  | 6 | EA
- Pressure Transmitter |  | 2 | EA
- Piping & Support |  | 1 | LOT
소 계 |  |  |  |  | 72000000 |  | 72000000 |  | 0 |  | 0
3-3. Distribution Module Skid
1) Distribution Module Skid |  | 2 | LOT | 45000000 | 90000000 | 45000000 | 90000000 |  | 0 |  | 0
- Pneumatic On-off Ball Valve |  | 1 | EA
- Flow meter for Air & Chem |  | 20 | EA
- Diaphragm Pressure Gauge | 0-10 bar | 20 | EA
- PRV for Air | 0-10 bar | 10 | EA
- Pressure Gauge | 0-10 bar | 20 | EA
- Ring Blower |  | 2 | EA
- Piping & Support |  | 1 | LOT
소 계 |  |  |  |  | 90000000 |  | 90000000 |  | 0 |  | 0
3-4. Direct Injector
- Direct Injection Nozzle |  | 20 | LOT | 6000000 | 120000000 | 6000000 | 120000000 |  | 0 |  | 0
소 계 |  |  |  |  | 120000000 |  | 120000000 |  | 0 |  | 0
합 계 |  |  |  |  | 282000000 |  | 282000000 |  | 0 |  | 0
4. Electric & Instrument
4-1. Electric Work
1) DCS Modification | 한국에머슨 | 1 | LOT | 60000000 | 60000000 | 60000000 | 60000000 | 0 | 0 | 0 | 0
2) Instrument Cabinets |  | 1 | LOT | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
소 계 |  |  |  |  | 60000000 |  | 60000000 |  | 0 |  | 0
합 계 |  |  |  |  | 60000000 |  | 60000000 |  | 0 |  | 0
5. Bulk Material
5-1. Thermal Insulation & Lagging
1) Ammonia Storage & Supply System |  | 1 | LOT | 32000000 | 32000000 | 32000000 | 32000000 | 0 | 0 | 0 | 0
- Pump 등 기타 |  | 50 | m2
- 배관 |  | 200 | m2
소 계 |  |  |  |  | 32000000 |  | 32000000 |  | 0 |  | 0
5-2. Piping & Valves Support Material
1) Manual Valve Unit |  | 1 | LOT | 22000000 | 22000000 | 22000000 | 22000000 | 0 | 0 | 0 | 0
2) Loose Piping Material |  | 1 | LOT | 12000000 | 12000000 | 12000000 | 12000000 | 0 | 0 | 0 | 0
3) Hanger & Support |  | 1 | LOT | 3000000 | 3000000 | 3000000 | 3000000 | 0 | 0 | 0 | 0
소 계 |  |  |  |  | 37000000 |  | 37000000 |  | 0 |  | 0
5-3. Electrical Work & Instrument Work
1) Electrical Work & Instrument Work |  | 1 | LOT | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
- Cable Tray & Conduit Work |  | 1 | LOT
- Power Cable Work |  | 1 | LOT
- Signal & Control Cable Work |  | 1 | LOT
- Electric Tracing |  | 1 | LOT
- Instrument Hook-up Material |  | 1 | LOT
소 계 |  |  |  |  | 0 |  | 0 |  | 0 |  | 0
합 계 |  |  |  |  | 69000000 |  | 69000000 |  | 0 |  | 0
6. Miscellaneous
1) Embedded Materials |  | 1 | LOT | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2) Spare Part for Commissioning&Erection |  | 1 | LOT | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3) Special Tools |  | 1 | LOT | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4) Safety Equipment | Mask, etc | 1 | SET | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1) Commissioning Fee | 자가측정 | 2 | SET | 2000000 | 4000000 | 2000000 | 4000000 | 0 | 0 | 0 | 0
2) Packing & Inspection |  | 1 | LOT | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
합 계 |  |  |  |  | 4000000 |  | 4000000 |  | 0 |  | 0
7. Emgineering Service
1) Basic Engineering |  | 1 | LOT | 15000000 | 15000000 | 0 | 0 | 0 | 0 | 15000000 | 15000000
2) Equipment Engineering |  | 1 | LOT | 50000000 | 50000000 | 0 | 0 | 0 | 0 | 50000000 | 50000000
- CFD, etc |  | 1 | LOT
3) Piping Engineering |  | 1 | LOT | 15000000 | 15000000 | 0 | 0 | 0 | 0 | 15000000 | 15000000
4) Control & Electric Engineering |  | 1 | LOT | 15000000 | 15000000 | 0 | 0 | 0 | 0 | 15000000 | 15000000
5) Civil Engineering |  | 1 | LOT | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
합 계 |  |  |  |  | 95000000 |  | 0 |  | 0 |  | 95000000
8. Installation Fee
1) Equipment & Piping Work |  | 2 | LOT | 147320000 | 294640000 |  | 61385000 |  | 45000000 |  | 188255000 | 추석 연휴 Tie-In 공사 포함
2) E&I Work |  | 2 | LOT | 48000000 | 96000000 | 23000000 | 46000000 | 24000000 | 48000000 | 1000000 | 2000000
3) 현장 관리비 |  | 1 | LOT | 31000000 | 31000000 | 0 | 0 | 0 | 0 | 31000000 | 31000000
합 계 |  |  |  |  | 421640000 |  | 107385000 |  | 93000000 | 32000000 | 221255000
직 접 공 사 비 계 |  |  |  |  | 931640000 |  | 522385000 |  | 93000000 |  | 316255000
0
0
0
0
De-Nox 설비 설치공사 견적 내역서
De-Nox 설비 설치공사 견적 내역서
통영에코파워 SCR 환경설비 개선 제안 (Direct Injection System)

## 실행예산서
-프로젝트 종료시까지 예산을 사용 에정으로 표기한것임,
■ 실행예산서 - HRSG #11, #12 SCR 환원제 직접 분사 설비 설치 공사 - 26년 1월 마감
항목 | 업체명 | 계정명 | 입찰 견적 (2025.08.19) A | 최초 실행원가 (2025-09-29) B | 집행금액 |  |  | 증감 (e-B) | 비고
[5 empty] | 1월마감 c | 집행예정 d | 계 (c+d)=e | [6 empty] | 합계 | 2025년 8월 | 9월 | 10월 | 11월 | 12월 | 26년 1월 | 2월 | 3월 | 4월 | 5월 | 6월 | 7월 | 8월
외주가공비-설비(도급) |  |  | 884350000 | 808922210 | 266100000 | 497400000 | 763500000 | -45422210 |  | -75427790 |  |  |  | 0
Module 제작 | 에스에이치씨 | 외주가공비-설비(도급) | 72000000 | 71000000 | 14200000 | 56800000 | 71000000 | 0 | 제작 외주 |  | 서해플랜트 | 380000000 | 342000000 | 14200000 |  |  |  |  | 14200000 |  |  |  | 56800000
Injector | - | 외주가공비-설비(도급) | 80000000 | 78000000 | 0 | 78000000 | 78000000 | 0 | 제작 외주, 22 sets (spare 포함) |  | 원플랜트 | 80000000 | 72000000 | 0 | [8 empty] | 78000000
현장 설치비 (기계,배관) | 미래종합기술 | 외주가공비-설비(도급) | 311000000 | 288000000 | 117500000 | 117500000 | 235000000 | -53000000 | 현장 공사, Tie-In S/D 포함 (추석연휴기간), 보온 분리(추후선정) | 235000000 | Ijector | 88000000 | 79200000 | 117500000 |  |  | 23500000 | 94000000 |  |  | 117500000
현장 설치비 (보온) | 추후선정 | 외주가공비-설비(도급) |  |  | 0 | 40000000 | 40000000 | 40000000 | 보온 분리(추후선정) |  | Ijector | 88000000 | 79200000 | 0 | [8 empty] | 40000000
Auto Valves | 주영씨엔에스 | 외주가공비-설비(도급) | 75000000 | 68922210 | 61300000 | 6100000 | 67400000 | -1522210 |  | 61000000 | 대청테크놀로지 | 329000000 | 296100000 | 61300000 |  |  |  | 6100000 |  | 55200000 |  |  | 6100000
Instruments | - | 외주가공비-설비(도급) | 200000000 | 180000000 | 0 | 0 | 0 | -180000000 | PDP Panel, Transmitter, Spare 등 포함 |  | 포커스제어기술 | 78000000 | 70200000 | 0
Instruments 1차 | 한국요꼬가와 | 외주가공비-설비(도급) |  |  | 55700000 | 6900000 | 62600000 | 62600000 |  | 69000000 | 포커스제어기술 | 78000000 | 70200000 | 55700000 |  |  |  | 6900000 |  | 48800000 |  |  | 6900000
PDP Panel | 대청테크놀로지 | 외주가공비-설비(도급) |  |  | 3300000 | 29700000 | 33000000 | 33000000 |  | 33000000 | 포커스제어기술 | 78000000 | 70200000 | 3300000 | [5 empty] | 3300000 | 26400000 | 3300000
현장 설치비 (전기계장) | 대청테크놀로지 | 외주가공비-설비(도급) | 96000000 | 82000000 | 14100000 | 126900000 | 141000000 | 59000000 | 현장 공사 | 141000000 | 한국 에머슨 | 53000000 | 50350000 | 14100000 | [5 empty] | 14100000 |  |  | 126900000
DCS Modification | 한국에머슨 | 외주가공비-설비(도급) | 50350000 | 41000000 | 0 | 35500000 | 35500000 | -5500000 | DCS AO Card 추가 및 Software 수정 | 35500000 |  |  |  | 0 | [8 empty] | 35500000
외주용역비 |  |  | 39500000 | 32500000 | 17000000 | 13300000 | 30300000 | -2200000 |  | -7000000 |  | 1252000000 |  | 0
대기환경측정 | - | 외주용역비-도급 | 4500000 | 4500000 | 0 | 4500000 | 4500000 | 0 | 전/후단 1회 측정 및 보고서 제출 |  |  |  |  | 0 | [8 empty] | 4500000
기계설계 등 | 미래종합기술 | 외주용역비-도급 | 15000000 | 10000000 | 0 | 8800000 | 8800000 | -1200000 | Injector 설치 부 상세설계 및 배관 iso 등 | 8800000 | 잡급 예산 편성(전기) | 3000000 |  | 0 | [6 empty] | 8800000
CFD | 성균관대학교산학협력단 | 외주용역비-도급 | 20000000 | 18000000 | 17000000 | 0 | 17000000 | -1000000 | 성균관 대학, CFD용역 (기존 CGN대산 base) | 17000000 |  |  |  | 17000000 | [5 empty] | 17000000
잡급 |  |  | 0 | 3000000 | 0 | 3000000 | 3000000 | 0 |  | 3000000 |  | 2047000000 |  | 0
일용직 노무비 | - | 잡급 | 0 | 3000000 | 0 | 3000000 | 3000000 | 0 | 전기파트 직접시공 잡급 |  |  |  |  | 0 | [8 empty] | 3000000
안전관리비 |  |  | 31000000 | 19000000 | 4899900 | 14100100 | 19000000 | 0 |  | -12000000 |  |  |  | 0
안전관리비 | - | 소모품비-안전용품 | 31000000 | 19000000 | 4899900 | 14100100 | 19000000 | 0 | 대상액 5억이상 50억 미만 / 요율 2.53% 적용 |  | 31443300 | 요율로 반영, 공사업체 금액에서 제외함. |  | 4899900 |  |  | 4899900 | [5 empty] | 14100100
경비 |  |  | 17630000 | 17630000 | 2980311 | 14649689 | 17630000 | 0 |  | 0 |  |  |  | 0
여비교통비(공사인원) | - | 여비교통비-국내 | 17630000 | 17630000 | 2339320 | 14649689 | 16989009 | -640991 | 2인/60일 기준 |  | 407000000 | 12820500 |  | 2339320 |  |  | 2089145 | 128010 | 27620 | 94545 |  |  | 14649689
현장 잡자재 구매 |  | 소모품비-기타 |  |  | 635991 | 0 | 635991 | 635991 | [5 empty] | 635991 |  |  | 635991
법인차량 |  | 차량유지비-수선비_법인차량 |  |  | 5000 | 0 | 5000 | 5000 | [5 empty] | 5000 | [5 empty] | 5000
보험료-보증 |  |  | 1250000 | 1250000 | 765930 | 1250000 | 2015930 | 765930 |  | 0 |  |  |  | 0
계약금보증보험 | - | 보험료-보증 | 150000 | 150000 | 566530 | 150000 | 716530 | 566530 | 계약금액의 10% |  |  |  |  | 566530 |  |  |  | 243920 | 322610 |  |  |  | 150000
선급금보증보험 | - | 보험료-보증 | 300000 | 300000 | 0 | 300000 | 300000 | 0 | 계약금액의 10% |  | 1000000000 |  |  | 0 | [8 empty] | 300000
하자이행보증보험 | - | 보험료-보증 | 800000 | 800000 | 0 | 800000 | 800000 | 0 | 계약금액의 10% (하자이행기간 36개월) |  | 0 |  |  | 0 | [8 empty] | 800000
하도급대금보증보험 | - | 보험료-보증 |  | 0 | 199400 | 0 | 199400 | 199400 |  |  | 50000000 |  |  | 199400 |  |  | 199400
예비비 |  |  | 21470000 | 10000000 | 0 | 10000000 | 10000000 | 0 |  | -11470000 |  |  |  | 0
예비비 | - | 예비비 | 21470000 | 10000000 | 0 | 10000000 | 10000000 | 0 | 수주금액의 1.2% |  |  |  |  | 0 | [8 empty] | 10000000
돌관작업비 | - | 예비비 |  | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0
기타비 |  |  | 3000000 | 3000000 | 0 | 3000000 | 3000000 | 0 |  | 0 |  |  |  | 0
현장사무실 | - | 지급임차료-기타 | 3000000 | 3000000 | 0 | 3000000 | 3000000 | 0 | [5 empty] | 0 | [8 empty] | 3000000
직접원가 합계 |  |  | 998200000 | 895302210 | 291746141 | 556699789 | 848445930 | -46856280 |  | -102897790 |  |  |  | 0
제조간접비 |  |  | 49450000 | #REF! | 0 | 40227790 | 40227790 | #REF! | [5 empty] | 0
관리자 급여 외 | #REF! | 제조간접비 | 49450000 | #REF! | 0 | 40227790 | 40227790 | #REF! | [5 empty] | 0 | [8 empty] | 40227790
※ 집행예정
-프로젝트 종료시까지 예산을 사용 에정으로 표기한것임,
※검증
[5 empty] | 마감기준 원가 | 291746141
[5 empty] | 간접비 누계 | 0
[5 empty] | 마감기준 직접원가 | 291746141 | TRUE
(원가 - 간접비 누계)=
0

## 협력업체 기성금신청 1안 (hidden)
폰트 : 10, 본문 행 높이 :20, 구분 라인 행 높이 : 15, 박스기준은 "2.결제조건"사이즈 기준으로 좌우 대칭 맞출것
1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
통영에코파워 프로젝트 관련하여 협력업체 기성금 지급을 아래와 같이 지급하고자 하오니 재가하여
주시기 바랍니다.
- 아 래 -
1. 프로젝트 명 : 통영에코파워 / HRSG#11, #12 SCR 환원제 직접 분사 설비 설치 공사
2. 수주금액/프로젝트 코드 : 935,530,000원 / PASC0IT20250011
| 3. 협력업체 기성금 신청내역 | [52 empty] | (단위: 원 VAT 별도)
|  | 업체명 | [11 empty] | 계약품목 | [10 empty] | 발주금액 | [9 empty] | 금회기성 | [9 empty] | 누계기성 | [9 empty] | 잔여기성
|  | 주영씨엔에스 | [11 empty] | Auto Valve | [10 empty] | 61000000 | [9 empty] | 6100000 | [9 empty] | 61000000 | [9 empty] | -
[25 empty] | 100% | [9 empty] | 10% | [9 empty] | 100% | [9 empty] | 0%
|  | 한국요꼬가와전기 | [11 empty] | Instrument | [10 empty] | 69000000 | [9 empty] | 6900000 | [9 empty] | 69000000 | [9 empty] | -
[25 empty] | 100% | [9 empty] | 10% | [9 empty] | 100% | [9 empty] | 0%
|  | 미래종합기술 | [11 empty] | 배관 ISO 작성 외 | [10 empty] | 8800000 | [9 empty] | 8800000 | [9 empty] | 8800000 | [9 empty] | -
[25 empty] | 100% | [9 empty] | 100% | [9 empty] | 100% | [9 empty] | 0%
4. 기타사항
1) 계정 코드 및 코스트센터 : 외주가공비-설비(도급) 외 / 플랜트대기파트
2) 공정 진행률에 따른 기성금 지급
| 5. 프로젝트 비용현황 | [47 empty] | (단위: 원 VAT 별도)
|  | 업체명 | [11 empty] | 계약품목 | [10 empty] | 발주금액 | [9 empty] | 금회 | [9 empty] | 전월 누계 | [9 empty] | 잔여 | [9 empty] | 계약일 | 종료일 | 착공일 | 준공일 | 업체명 | 비고
|  |  |  | 에스에이치씨 | [9 empty] | Module 제작 | [10 empty] | 71000000 | [9 empty] | 49700000 | [9 empty] | 14200000 | [9 empty] | 7100000
|  |  |  | 미래종합기술 | [9 empty] | 기계,배관 설치 | [10 empty] | 235000000 | [9 empty] | 70500000 | [9 empty] | 117500000 | [9 empty] | 47000000
|  |  |  | 주영씨엔에스 | [9 empty] | Auto Valves | [10 empty] | 61000000 | [9 empty] | 6100000 | [9 empty] | 54900000 | [9 empty] | 0
|  |  |  | 한국요꼬가와 | [9 empty] | Instruments 1차 | [10 empty] | 69000000 | [29 empty] | 69000000
|  |  |  | 대청테크놀로지 | [9 empty] | PDP Panel | [10 empty] | 33000000 | [29 empty] | 33000000
|  |  |  | 대청테크놀로지 | [9 empty] | 전기계장 설치 | [10 empty] | 141000000 | [29 empty] | 141000000
|  |  |  | 한국에머슨 | [9 empty] | DCS Modification | [10 empty] | 35500000 | [29 empty] | 35500000
|  | 외주가공비-설비(도급) 합계 | [22 empty] | 645500000 | [9 empty] | 126300000 | [9 empty] | 186600000 | [9 empty] | 332600000
|  |  |  | 기계설계 등 | [9 empty] | 미래종합기술 | [10 empty] | 8800000
|  |  |  | CFD | [9 empty] | 성균관대학교 | [10 empty] | 17000000
|  | 외주용역비-도급 합계 | [22 empty] | 25800000 | [9 empty] | 0 | [9 empty] | 0 | [9 empty] | 0
여비교통비
차량유지비-수선비-법인차량
소모품비-안전용품
지급수수료-기타
보험료-보증
지급수수료-기타
1월 마감기준 합계
| 6. 자금수지 현황 | [52 empty] | (단위: 원 VAT 별도)
|  | 구분 | [11 empty] | 고객사 기성금(A) | [11 empty] | 지출(B) | [11 empty] | 차이(A-B) | [11 empty] | 비고
|  | 누계 |  |  |  | 26년 1월 | [7 empty] | 93553000 | [11 empty] | 291746141 | [11 empty] | -198193141 | [11 empty] | -
|  | 신청 |  |  |  | 26년 2월 | [7 empty] | 0 | [11 empty] | 168400000 | [11 empty] | -168400000
|  | 예정 |  |  |  | 26년 3월 | [7 empty] | 467765000 | [23 empty] | 467765000 | [11 empty] | -
[6 empty] | 26년 4월 | [31 empty] | 0 | [11 empty] | -
[6 empty] | 26년 5월 | [31 empty] | 0 | [11 empty] | -
[6 empty] | 26년 6월 | [31 empty] | 0 | [11 empty] | -
[6 empty] | 26년 7월 | [31 empty] | 0 | [11 empty] | -
[6 empty] | 26년 8월 | [31 empty] | 0 | [11 empty] | -
[6 empty] | 26년 9월 | [31 empty] | 0 | [11 empty] | -
[6 empty] | 26년 10월 | [31 empty] | 0 | [11 empty] | -
[6 empty] | 26년 11월 | [31 empty] | 0 | [11 empty] | -
[6 empty] | 26년 12월 | [31 empty] | 0 | [11 empty] | -
|  | 누계 | [11 empty] | 561318000 | [11 empty] | 460146141 | [11 empty] | 101171859 | [11 empty] | -
* 3월 납품 완료 후 50% / 4월 성능시험 및 준공완료 후 40% 신청 예정
7. 붙임
1) 26년 2월 기성금 신청서_통영에코파워_주영씨앤에스(I&C밸브)_잔금10% - 1부
2) 26년 2월 기성금 신청서_통영에코파워_한국요꼬가와전기(Instrument)_잔금10% - 1부
3) 26년 2월 기성금신청서_통영에코파워 배관 ISO 작성 외_미래종합기술(잔금100%) - 1부