## 대기+수처리+헝가리
영업3팀 (대기+수처리+헝가리법인)
3. '26년 계획대비 차이
구분 | '26년 계획(A) | [6 empty] | '26년 예상(B) | [6 empty] | 차이 B-A
| 대기 |  | 수처리 |  | 헝가리법인 | 함계 |  | 대기 |  | 수처리 |  | 헝가리법인 | 함계 |  | 대기 |  | 수처리 |  | 헝가리법인 | 함계
'26년 매출반영 | 44247000000 | 100% | 16982490371.5156 | 100% |  | 61229490371.5156 | 100% | 67373686852 | 100% | 16339092620 | 100% |  | 83712779472 | 100% | 23126686852 | 36.72% | -643397751.5156 | 100% |  | 22483289100.4844 | 52.27%
'26년 제조간접원가 | 2432297221.642 | 5.497% | 1256704287.4922 | 7.4% |  | 3689001509.1342 | 5.497% | 3567384510.503 | 5.295% | 977073522.53 | 5.98% |  | 4544458033.033 | 5.497% | 1135087288.861 | 23.19% | -279630764.9622 | 5.497% |  | 855456523.8988 | 46.67%
'26년 제조원가 | 39639494173.812 | 89.59% | 15145215296.3441 | 89.18% |  | 54784709470.1561 | 89.47% | 61121338717.1046 | 90.72% | 14668117288.6865 | 89.77% |  | 75789456005.7912 | 90.54% | 21481844543.2926 | 38.34% | -477098007.6575 | 74.15% |  | 21004746535.6351 | 54.19%
'26년 매출총이익 | 4607505826.188 | 10.41% | 1837275075.1716 | 10.82% |  | 6444780901.3596 | 10.53% | 6252348134.8954 | 9.28% | 1670975331.3135 | 10.23% |  | 7923323466.2088 | 9.465% | 1644842308.7074 | 22.94% | -166299743.8581 | 25.85% |  | 1478542564.8493 | 35.7%
'26년 판관비( C) | 5442381000 | 12.3% | 2275653709.7831 | 13.4% |  | 7718034709.7831 | 12.3% | 8286963482.796 | 12.3% | 2189438411.08 | 13.4% |  | 10476401893.876 | 12.3% | 2844582482.796 | 35.74% | -86215298.7031 | 12.3% |  | 2758367184.0929 | 52.27%
'26년 영업이익( D) | -834875173.812 | -1.887% | -438378634.6115 | -2.581% | 0 | -1273253808.4235 | -2.079% | -2034615347.9006 | -3.02% | -518463079.7665 | -3.173% |  | -2553078427.6672 | -3.05% | -1199740174.0886 | 100.5% | -80084445.155 | 12.45% |  | -1279824619.2436 | 143.7%
손익분기 판관비 부담 (C+D, 영업이익 < 0) | 4607505826.188 |  | 1837275075.1716 |  | 0 | 6444780901.3596 |  | 6252348134.8954 |  | 1670975331.3135 |  |  | 7923323466.2088 |  | 1644842308.7074 |  | -166299743.8581 |  | 0 | 1478542564.8493
'26년 증분이익 | 7039803047.83 |  | 3093979362.6638 |  | 0 | 10133782410.4938 |  | 9819732645.3984 |  | 2648048853.8435 |  | 0 | 12467781499.2418 |  | 2779929597.5684 |  | -445930508.8203 |  | 0 | 2333999088.7481
2.788%
■ 수주완료/확정 ■ 수주 기대 ■ 입찰 경쟁 ■ 투자 미정
■ 수주완료/확정 ■ 수주 기대 ■ 입찰 경쟁 ■ 투자 미정

## 대기
대기방지
| '25년 수주잔고 => | [21 empty] | '26년 수주 =>
1. 프로젝트별 세부내역 | PASC0IB20250011 |  | PABF0IK20250011 |  | PABF1IE20230011 |  | PASC0IT20250011 |  | PAAC0IE20250011 |  | PAAE0IC20230011 |  | PASC0IB20240011 |  | PACC0EK20050011 |  | PAAE0IE20250011 |  | PADH0IE20250011 |  | PASC0IP20220011 | [40 empty] | (단위 : 원/VAT별도)
구분 | BHI / QATAR FACILITY E IWPP SCR SYSTEM |  | KTC / EV용 화재안전성센터 대방설비 설치공사 |  | BM HU / [EA1] 환경설비 납품, 설치 및 시운전 공사 |  | 통영에코파워 / HRSG #11, #12 SCR 환원제 직접 분사 설비 설치 공사 |  | 에코프로머티리얼즈 / [4캠퍼스] CPM3 SCRUBBER 납품 및 설치공사 |  | CGN대산전력 / Air Pollution Control System 공급 및 설치계약 |  | 비에이치아이 / Amiral Cogen IPP PJT/SCR/YPES (HG) |  | 광림 / 특장도장동 환경설비 연간유지보수 |  | 에코프로비엠 / 고체전해질PP 라인 대기오염방지설비 소음기 설치 건 |  | 에코프로비엠 / 오창 환경사업장 3F 제습 설비 보완 공사 |  | 포스코 / (포항)1전강 2COF SCR 신설(설비단독,내자) 외 1건 |  | BHI 대만 튱샤오 HRSG SCR PKG |  | KCL(삼척) 화재센터 ACT |  | 에코프로INNO HU LHM8K IPPC |  | 도레이첨단소재(구미) BF+SCR |  | BHI 포스코(포항) LNG복합 |  | 유한화학(화성) RTO 신규 |  | 삼천포발전본부 SCR 개선 |  | 한국소방산업기술원 환경설비 |  | 한주(울산)_SCR |  | 동서발전(음성) #2 복합발전 |  | 와이엔텍(여수) |  | 삼표시멘트(삼척) |  | 여주축협(여주) |  | 중부발전(용인) |  | LG화학(여수) |  | 동서발전(여수) |  | 오성테크놀로지(익산) |  | 금강씨엔티(동해) |  | 북산환경(안산) |  | 합 계
계약예정일 | 25년 6월 - 26년 6월 |  | 25년 6월 - 26년 9월 |  | 23년 2월 - 26년 12월 |  | 25년 10월 - 26년 4월 |  | 25년 8월 - 26년 5월 |  | 23년 11월 - 26년 9월 |  | 24년 10월 - 25년 9월 |  | 25년 5월 - 26년 4월 |  | 25년 11월 - 26년 1월 |  | 25년 8월 - 25년 11월 |  | 22년 8월 - 25년 1월 |  | 26년 3월 |  | 26년 2월 |  | 26년 2월 |  | 26년 3월 |  | 26년 4월 |  | 26년 4월 |  | 26년 5월 |  | 26년 7월 |  | 26년 10월 |  | 26년 9월 |  | 26년 10월 |  | 26년 9월 |  | 26년 9월 |  | 26년 10월 |  | 26년 10월 |  | 26년 10월 |  | 26년 9월 |  | 26년 4월 |  | 26년 7월
계약예정금액 | 2741193600 | 100% | 1793293440 | 100% | 1232485613 | 100% | 782283637 | 100% | 407388150 | 100% | 161695500 | 100% | 118000000 | 100% | 40900000 | 100% | 32000000 | 100% | 30516912 | 100% | 8730000 | 100% | 23350000000 | 100% | 4000000000 | 100% | 374550000 | 100% | 3200000000 | 100% | 7386500000 | 100% | 3990000000 | 100% | 2460000000 | 100% | 1629000000 | 100% | 3000000000 | 100% | 8000000000 | 100% | 30000000000 | 100% | 15000000000 | 100% | 44000000000 | 100% | 19000000000 | 100% | 2500000000 | 100% | 19000000000 | 100% | 4000000000 | 100% | 1000000000 | 100% | 20000000000 | 100% | 219238536852
최대 Nego 금액 | [23 empty] | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% | 2214000000 | 90% | 1466100000 | 90% | 2700000000 | 90% | 7200000000 | 90% | 27000000000 | 90% | 13500000000 | 90% | 39600000000 | 90% | 17100000000 | 90% | 2250000000 | 90% | 17100000000 | 90% | 3600000000 | 90% | 900000000 | 90% | 18000000000 | 90% | 152630100000
프로젝트 진행률 (2026년 기준) | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 30% |  | 100% |  | 100% |  | 100% |  | 10% |  | 100% |  | 30% |  | 100% |  | 10% |  | 30% |  | 20% |  | 20% |  | 20% |  | 20% |  | 50% |  | 20% |  | 100% |  | 100% |  | 20%
기계 |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% | 2420000000 |  | 1020000000 | 25.5% | 140669100 | 37.56% | 1789010000 | 55.91% | 2002700000 | 27.11% | 2400000000 | 60.15% | 1520000000 | 61.79% | 874000000 | 53.65% | 1900000000 | 63.33% | 2300000000 | 28.75% | 27000000000 | 90% | 13500000000 | 90% | 35200000000 | 80% | 16150000000 | 85% | 2125000000 | 85% | 16150000000 | 85% | 3200000000 | 80% | 900000000 | 90% | 17000000000 | 85%
전기 |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% | 270000000 |  | 214000000 | 5.35% | 49995000 | 13.35% | 399900000 | 12.5% | 390600000 | 5.288% |  | 0% | 220000000 | 8.943% | 218000000 | 13.38% | 220000000 | 7.333% | 410000000 | 5.125% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0%
계장 |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% | 325000000 |  |  | 0% |  | 0% |  | 0% | 350505000 | 4.745% |  | 0% |  | 0% |  | 0% |  | 0% | 320000000 | 4% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0%
배관 |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% | 195000000 | 4.887% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0%
회전기기 |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% | 330000000 | 1.413% | 170000000 | 4.25% |  | 0% | 146300000 | 4.572% | 234000000 | 3.168% | 320000000 | 8.02% |  | 0% | 94000000 | 5.77% |  | 0% | 150000000 | 1.875% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0%
열교환기 |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% | 649000000 | 16.23% |  | 0% |  | 0% |  | 0% | 240000000 | 6.015% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0%
촉매 |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% | 15300000000 | 65.52% |  | 0% |  | 0% | 67890000 | 2.122% | 2986500000 | 40.43% |  | 0% |  | 0% |  | 0% |  | 0% | 2550000000 | 31.87% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0%
분석기 |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% | 1780000000 |  |  | 0% |  | 0% | 106700000 | 3.334% | 423000000 | 5.727% |  | 0% |  | 0% |  | 0% |  | 0% | 360000000 | 4.5% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0%
버너 |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% | 23750000 | 0.7422% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0%
Filter |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% | 550000000 | 13.75% | 52800000 | 14.1% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0%
활성탄 |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% | 250000000 | 6.25% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% | 19200000 | 1.179% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0%
방음룸 |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% | 120000000 | 3% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0%
안전관리비 |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% | 30000000 | 0.75% |  | 0% | 25000000 | 0.7812% |  | 0% | 40000000 | 1.003% | 45000000 | 1.829% |  | 0% | 55000000 | 1.833% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0%
외주용역 |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% | 390000000 | 1.67% |  | 0% |  | 0% | 15000000 | 0.4688% | 289620000 | 3.921% | 125000000 | 3.133% | 71000000 | 2.886% | 20000000 | 1.228% | 80000000 | 2.667% | 280000000 | 3.5% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0%
기타 |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% | 821000000 | 3.516% | 105000000 | 2.625% | 60756000 | 16.22% | 45000000 | 1.406% | 163200000 | 2.209% | 275000000 | 6.892% | 26500000 | 1.077% | 98000000 | 6.016% |  | 0% | 180000000 | 2.25% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0%
이자비용 |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0%
제조직접원가 | 2449566551.04 | 89.36% | 1556149874.88 | 86.78% | 1061544047.3911 | 86.13% | 748645440.609 | 95.7% | 344899682.52 | 84.66% | 143431038.6561 | 88.7% | 118000000 | 100% | 32100000 | 78.48% | 25867420 | 80.84% | 24878345.6218 | 81.52% | 7339205.8836 | 84.07% | 21636000000 | 92.66% | 3108000000 | 77.7% | 304220100 | 81.22% | 2618550000 | 81.83% | 6840125000 | 92.6% | 3595000000 | 90.1% | 1882500000 | 76.52% | 1323200000 | 81.23% | 2255000000 | 75.17% | 6550000000 | 81.88% | 27000000000 | 90% | 13500000000 | 90% | 35200000000 | 80% | 16150000000 | 85% | 2125000000 | 85% | 16150000000 | 85% | 3200000000 | 80% | 900000000 | 90% | 17000000000 | 85% | 187850016706.6016
제조간접원가 | 117871324.8 | 4.3% | 77111617.92 | 4.3% | 2464971.226 | 0.2% | 33638196.391 | 4.3% | 17517690.45 | 4.3% | 12127162.5 | 7.5% | 0 | 0% | 1758700 | 4.3% | 1376000 | 4.3% | 1312227.216 | 4.3% | 820620 | 9.4% | 1284250000 | 5.5% | 220000000 | 5.5% | 20600250 | 5.5% | 176000000 | 5.5% | 406257500 | 5.5% | 219450000 | 5.5% | 135300000 | 5.5% | 89595000 | 5.5% | 165000000 | 5.5% | 440000000 | 5.5% | 1650000000 | 5.5% | 825000000 | 5.5% | 2420000000 | 5.5% | 1045000000 | 5.5% | 137500000 | 5.5% | 1045000000 | 5.5% | 220000000 | 5.5% | 55000000 | 5.5% | 1100000000 | 5.5% | 11919951260.503
제조원가 | 2567437875.84 | 93.66% | 1633261492.8 | 91.08% | 1064009018.6171 | 86.33% | 782283637 | 100% | 362417372.97 | 88.96% | 155558201.1561 | 96.2% | 118000000 | 100% | 33858700 | 82.78% | 27243420 | 85.14% | 26190572.8378 | 85.82% | 8159825.8836 | 93.47% | 22920250000 | 98.16% | 3328000000 | 83.2% | 324820350 | 86.72% | 2794550000 | 87.33% | 7246382500 | 98.1% | 3814450000 | 95.6% | 2017800000 | 82.02% | 1412795000 | 86.73% | 2420000000 | 80.67% | 6990000000 | 87.38% | 28650000000 | 95.5% | 14325000000 | 95.5% | 37620000000 | 85.5% | 17195000000 | 90.5% | 2262500000 | 90.5% | 17195000000 | 90.5% | 3420000000 | 85.5% | 955000000 | 95.5% | 18100000000 | 90.5% | 199769967967.1046
판관비 | 337166812.8 | 12.3% | 220575093.12 | 12.3% | 151595730.399 | 12.3% | 96220887.351 | 12.3% | 50108742.45 | 12.3% | 19888546.5 | 12.3% | 14514000 | 12.3% | 5030700 | 12.3% | 3936000 | 12.3% | 3753580.176 | 12.3% | 1073790 | 12.3% | 2872050000 | 12.3% | 492000000 | 12.3% | 46069650 | 12.3% | 393600000 | 12.3% | 908539500 | 12.3% | 490770000 | 12.3% | 302580000 | 12.3% | 200367000 | 12.3% | 369000000 | 12.3% | 984000000 | 12.3% | 3690000000 | 12.3% | 1845000000 | 12.3% | 5412000000 | 12.3% | 2337000000 | 12.3% | 307500000 | 12.3% | 2337000000 | 12.3% | 492000000 | 12.3% | 123000000 | 12.3% | 2460000000 | 12.3% | 26966340032.796
영업이익 | -163411088.64 | -5.961% | -60543145.92 | -3.376% | 16880863.9839 | 1.37% | -96220887.351 | -12.3% | -5137965.42 | -1.261% | -13751247.6561 | -8.504% | -14514000 | -12.3% | 2010600 | 4.916% | 820580 | 2.564% | 572758.9862 | 1.877% | -503615.8836 | -5.769% | -2442300000 | -10.46% | 180000000 | 4.5% | 3660000 | 0.9772% | 11850000 | 0.3703% | -768422000 | -10.4% | -315220000 | -7.9% | 139620000 | 5.676% | 15838000 | 0.9723% | 211000000 | 7.033% | 26000000 | 0.325% | -2340000000 | -7.8% | -1170000000 | -7.8% | 968000000 | 2.2% | -532000000 | -2.8% | -70000000 | -2.8% | -532000000 | -2.8% | 88000000 | 2.2% | -78000000 | -7.8% | -560000000 | -2.8% | -7497771147.9006
[23 empty] | 1714000000 | 7.34%
2. '26년 프로젝트별 손익
'26년 매출반영 | 2741193600 | 100% | 1793293440 | 100% | 1232485613 | 100% | 782283637 | 100% | 407388150 | 100% | 161695500 | 100% | 118000000 | 100% | 40900000 | 100% | 32000000 | 100% | 30516912 | 100% | 8730000 | 100% | 7005000000 | 100% | 4000000000 | 100% | 374550000 | 100% | 3200000000 | 100% | 738650000 | 100% | 3990000000 | 100% | 738000000 | 100% | 1629000000 | 100% | 300000000 | 100% | 2400000000 | 100% | 6000000000 | 100% | 3000000000 | 100% | 8800000000 | 100% | 3800000000 | 100% | 1250000000 | 100% | 3800000000 | 100% | 4000000000 | 100% | 1000000000 | 100% | 4000000000 | 100% | 67373686852 | 100%
'26년 제조간접원가 | 117871324.8 | 4.3% | 77111617.92 | 4.3% | 2464971.226 | 0.2% | 33638196.391 | 4.3% | 17517690.45 | 4.3% | 12127162.5 | 7.5% | 0 | 0% | 1758700 | 4.3% | 1376000 | 4.3% | 1312227.216 | 4.3% | 820620 | 9.4% | 385275000 | 5.5% | 220000000 | 5.5% | 20600250 | 5.5% | 176000000 | 5.5% | 40625750 | 5.5% | 219450000 | 5.5% | 40590000 | 5.5% | 89595000 | 5.5% | 16500000 | 5.5% | 132000000 | 5.5% | 330000000 | 5.5% | 165000000 | 5.5% | 484000000 | 5.5% | 209000000 | 5.5% | 68750000 | 5.5% | 209000000 | 5.5% | 220000000 | 5.5% | 55000000 | 5.5% | 220000000 | 5.5% | 3567384510.503 | 5.295%
'26년 제조원가 | 2567437875.84 | 93.66% | 1633261492.8 | 91.08% | 1064009018.6171 | 86.33% | 782283637 | 100% | 362417372.97 | 88.96% | 155558201.1561 | 96.2% | 118000000 | 100% | 33858700 | 82.78% | 27243420 | 85.14% | 26190572.8378 | 85.82% | 8159825.8836 | 93.47% | 6876075000 | 98.16% | 3328000000 | 83.2% | 324820350 | 86.72% | 2794550000 | 87.33% | 724638250 | 98.1% | 3814450000 | 95.6% | 605340000 | 82.02% | 1412795000 | 86.73% | 242000000 | 80.67% | 2097000000 | 87.38% | 5730000000 | 95.5% | 2865000000 | 95.5% | 7524000000 | 85.5% | 3439000000 | 90.5% | 1131250000 | 90.5% | 3439000000 | 90.5% | 3420000000 | 85.5% | 955000000 | 95.5% | 3620000000 | 90.5% | 61121338717.1046 | 90.72%
'26년 판관비 | 337166812.8 | 12.3% | 220575093.12 | 12.3% | 151595730.399 | 12.3% | 96220887.351 | 12.3% | 50108742.45 | 12.3% | 19888546.5 | 12.3% | 14514000 | 12.3% | 5030700 | 12.3% | 3936000 | 12.3% | 3753580.176 | 12.3% | 1073790 | 12.3% | 861615000 | 12.3% | 492000000 | 12.3% | 46069650 | 12.3% | 393600000 | 12.3% | 90853950 | 12.3% | 490770000 | 12.3% | 90774000 | 12.3% | 200367000 | 12.3% | 36900000 | 12.3% | 295200000 | 12.3% | 738000000 | 12.3% | 369000000 | 12.3% | 1082400000 | 12.3% | 467400000 | 12.3% | 153750000 | 12.3% | 467400000 | 12.3% | 492000000 | 12.3% | 123000000 | 12.3% | 492000000 | 12.3% | 8286963482.796 | 12.3%
'26년 영업이익 | -163411088.64 | -5.961% | -60543145.92 | -3.376% | 16880863.9839 | 1.37% | -96220887.351 | -12.3% | -5137965.42 | -1.261% | -13751247.6561 | -8.504% | -14514000 | -12.3% | 2010600 | 4.916% | 820580 | 2.564% | 572758.9862 | 1.877% | -503615.8836 | -5.769% | -732690000 | -10.46% | 180000000 | 4.5% | 3660000 | 0.9772% | 11850000 | 0.3703% | -76842200 | -10.4% | -315220000 | -7.9% | 41886000 | 5.676% | 15838000 | 0.9723% | 21100000 | 7.033% | 7800000 | 0.325% | -468000000 | -7.8% | -234000000 | -7.8% | 193600000 | 2.2% | -106400000 | -2.8% | -35000000 | -2.8% | -106400000 | -2.8% | 88000000 | 2.2% | -78000000 | -7.8% | -112000000 | -2.8% | -2034615347.9006 | -3.02%
514200000
3. '26년 계획대비 차이
구분 | '26년 계획(A) |  | '26년 예상(B) |  | 차이 B-A | B/A-1
'26년 매출반영 | 44247000000 | 100% | 67373686852 | 100% | 23126686852 | 52.27%
'26년 제조간접원가 | 2432297221.642 | 5.497% | 3567384510.503 | 5.497% | 1135087288.861 | 46.67%
'26년 제조원가 | 39639494173.812 | 89.59% | 61121338717.1046 | 90.72% | 21481844543.2926 | 54.19%
'26년 매출총이익 | 4607505826.188 | 10.41% | 6252348134.8954 | 9.28% | 1644842308.7074 | 35.7%
'26년 판관비( C) | 5442381000 | 12.3% | 8286963482.796 | 12.3% | 2844582482.796 | 52.27%
'26년 영업이익( D) | -834875173.812 | -1.887% | -2034615347.9006 | -3.02% | -1199740174.0886 | 143.7%
손익분기 판관비 부담 (C+D, 영업이익 < 0) | 4607505826.188 |  | 6252348134.8954 |  | 1644842308.7074
'26년 증분이익 | 7039803047.83 |  | 9819732645.3984 |  | 2779929597.5684
4.126%
■ 수주완료/확정 ■ 수주 기대 ■ 입찰 경쟁 ■ 투자 미정
■ 수주완료/확정 ■ 수주 기대 ■ 입찰 경쟁 ■ 투자 미정

## 수처리
수처리
| '25년 수주잔고 => | [7 empty] | '26년 수주 =>
1. 프로젝트별 세부내역 | [23 empty] | (단위 : 원/VAT별도)
구분 | 에코프로머티리얼즈 / 포항 4캠퍼스 머티리얼즈 통합폐수처리장 |  | 에코프로머티리얼즈 / 포항 4캠퍼스 통합폐수처리장 및 EWT 운영관리 |  | 에코프로이노베이션 / 증발농축 2단계 및 리튬용액 배관분리 공사 |  | BM HU / [EA1] 비공정 폐수 증발농축 시스템 납품 |  | [BMHU] 헝가리 EA1 Gray Water 처리 설비 |  | [BM] 포항 CAM9 LFP 공정 수/폐수처리설비 공사 |  | [덴티움] 암모니아 회수설비 공사 |  | [한화오션] 여수 집단에너지 폐수처리설비 공사 |  | [MAT] 포항 CPM1 폐수처리장 증설 공사 |  | [에스아이머티리얼즈] 실리콘 폐수 농축 설비 공사 |  | [BMHU] 헝가리 EA1 세탁폐수 처리 설비 설치 공사 |  | 합 계
계약예정일 | 23년 6월 - 26년 4월 |  | 25년 11월 - 26년 11월 |  | 24년 10월 - 26년 4월 |  | 24년 10월 - 26년 4월 |  | 26년 9월 |  | 26년 9월 |  | 26년 8월 |  | 26년 9월 |  | 26년 10월 |  | 26년 7월 |  | 26년 6월
계약예정금액 | 2345013300 | 100% | 1449708150 | 100% | 998832594 | 100% | 10988576 | 100% | 7000000000 | 100% | 3000000000 | 100% | 1750000000 | 100% | 8000000000 | 100% | 8000000000 | 100% | 4000000000 | 100% | 1034550000 | 100% | 37589092620
최대 Nego 금액 | [8 empty] | 6300000000 | 90% | 2700000000 | 90% | 1575000000 | 90% | 7200000000 | 90% | 7200000000 | 90% | 3600000000 | 90% | 931095000 | 90% | 29506095000
프로젝트 진행률 (2026년 기준) | 100% |  | 100% |  | 100% |  | 100% |  | 30% |  | 30% |  | 40% |  | 30% |  | 40% |  | 30% |  | 100%
토목 |  | 0% |  | 0% |  | 0% |  | 0% | 1875458462.6234 | 26.79% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% | 57678885 | 5.575%
기계 |  | 0% |  | 0% |  | 0% |  | 0% | 1105610014.1044 | 15.79% | 1200000000 | 40% | 898832000 | 51.36% | 2380000000 | 29.75% | 4096000000 | 51.2% | 2600000000 | 65% | 214099875 | 20.69%
전기 |  | 0% |  | 0% |  | 0% |  | 0% | 531079337.0945 | 7.587% | 420000000 | 14% | 143952000 | 8.226% | 1292000000 | 16.15% | 1200000000 | 15% | 160000000 | 4% | 94144545 | 9.1%
계장 |  | 0% |  | 0% |  | 0% |  | 0% | 0 | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0%
배관 |  | 0% |  | 0% |  | 0% |  | 0% | 652658674.189 | 9.324% | 650000000 | 21.67% | 128800000 | 7.36% | 2366400000 | 29.58% | 1040000000 | 13% | 180000000 | 4.5% | 65319210 | 6.314%
회전기기 |  | 0% |  | 0% |  | 0% |  | 0% | 0 | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0%
열교환기 |  | 0% |  | 0% |  | 0% |  | 0% | 0 | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0%
촉매 |  | 0% |  | 0% |  | 0% |  | 0% | 0 | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0%
분석기 |  | 0% |  | 0% |  | 0% |  | 0% | 0 | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0%
버너 |  | 0% |  | 0% |  | 0% |  | 0% | 0 | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0%
Filter |  | 0% |  | 0% |  | 0% |  | 0% | 0 | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0%
활성탄 |  | 0% |  | 0% |  | 0% |  | 0% | 0 | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0%
방음룸 |  | 0% |  | 0% |  | 0% |  | 0% | 0 | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0%
안전관리비 |  | 0% |  | 0% |  | 0% |  | 0% | 41466854.725 | 0.5924% | 46367000 | 1.546% | 24309521.6 | 1.389% | 119744480 | 1.497% | 128633600 | 1.608% | 41657333.3333 | 1.041% | 15000000 | 1.45%
외주용역 |  | 0% |  | 0% |  | 0% |  | 0% | 579795486.6008 | 8.283% | 60000000 | 2% | 50000000 | 2.857% | 40000000 | 0.5% | 128000000 | 1.6% | 20000000 | 0.5% | 255595230 | 24.71%
기타 |  | 0% |  | 0% |  | 0% |  | 0% | 1124788434.4147 | 16.07% | 88000000 | 2.933% | 122000000 | 6.971% | 650000000 | 8.125% | 240000000 | 3% | 125000000 | 3.125% | 131239830 | 12.69%
제조직접원가 | 2056839316.3493 | 87.71% | 1154046762.39 | 79.61% | 853279758.138 | 85.43% | 8581682.5137 | 78.1% | 5910857263.7518 | 84.44% | 2464367000 | 82.15% | 1367893521.6 | 78.17% | 6848144480 | 85.6% | 6832633600 | 85.41% | 3126657333.3333 | 78.17% | 833077575 | 80.53% | 31456378293.0761
제조간접원가 | 30485172.9 | 1.3% | 69585991.2 | 4.8% | 22973149.662 | 2.3% | 472508.768 | 4.3% | 518000000 | 7.4% | 222000000 | 7.4% | 129500000 | 7.4% | 592000000 | 7.4% | 592000000 | 7.4% | 296000000 | 7.4% | 76556700 | 7.4% | 2549573522.53
제조원가 | 2087324489.2493 | 89.01% | 1223632753.59 | 84.41% | 876252907.8 | 87.73% | 9054191.2817 | 82.4% | 6428857263.7518 | 91.84% | 2686367000 | 89.55% | 1497393521.6 | 85.57% | 7440144480 | 93% | 7424633600 | 92.81% | 3422657333.3333 | 85.57% | 909634275 | 87.93% | 34005951815.6061
판관비 | 314231782.2 | 13.4% | 194260892.1 | 13.4% | 133843567.596 | 13.4% | 1472469.184 | 13.4% | 938000000 | 13.4% | 402000000 | 13.4% | 234500000 | 13.4% | 1072000000 | 13.4% | 1072000000 | 13.4% | 536000000 | 13.4% | 138629700 | 13.4% | 5036938411.08
영업이익 | -56542971.4493 | -2.411% | 31814504.31 | 2.195% | -11263881.396 | -1.128% | 461915.5343 | 4.204% | -366857263.7518 | -5.241% | -88367000 | -2.946% | 18106478.4 | 1.035% | -512144480 | -6.402% | -496633600 | -6.208% | 41342666.6667 | 1.034% | -13713975 | -1.326% | -1453797606.6861
2. '26년 프로젝트별 손익
'26년 매출반영 | 2345013300 | 100% | 1449708150 | 100% | 998832594 | 100% | 10988576 | 100% | 2100000000 | 100% | 900000000 | 100% | 700000000 | 100% | 2400000000 | 100% | 3200000000 | 100% | 1200000000 | 100% | 1034550000 | 100% | 16339092620 | 100%
'26년 제조간접원가 | 30485172.9 | 1.3% | 69585991.2 | 4.8% | 22973149.662 | 2.3% | 472508.768 | 4.3% | 155400000 | 7.4% | 66600000 | 7.4% | 51800000 | 7.4% | 177600000 | 7.4% | 236800000 | 7.4% | 88800000 | 7.4% | 76556700 | 7.4% | 977073522.53 | 5.98%
'26년 제조원가 | 2087324489.2493 | 89.01% | 1223632753.59 | 84.41% | 876252907.8 | 87.73% | 9054191.2817 | 82.4% | 1928657179.1255 | 91.84% | 805910100 | 89.55% | 598957408.64 | 85.57% | 2232043344 | 93% | 2969853440 | 92.81% | 1026797200 | 85.57% | 909634275 | 87.93% | 14668117288.6865 | 89.77%
'26년 판관비 | 314231782.2 | 13.4% | 194260892.1 | 13.4% | 133843567.596 | 13.4% | 1472469.184 | 13.4% | 281400000 | 13.4% | 120600000 | 13.4% | 93800000 | 13.4% | 321600000 | 13.4% | 428800000 | 13.4% | 160800000 | 13.4% | 138629700 | 13.4% | 2189438411.08 | 13.4%
'26년 영업이익 | -56542971.4493 | -2.411% | 31814504.31 | 2.195% | -11263881.396 | -1.128% | 461915.5343 | 4.204% | -110057179.1255 | -5.241% | -26510100 | -2.946% | 7242591.36 | 1.035% | -153643344 | -6.402% | -198653440 | -6.208% | 12402800 | 1.034% | -13713975 | -1.326% | -518463079.7665 | -3.173%
3. '26년 계획대비 차이
구분 | '26년 계획(A) |  | '26년 예상(B) |  | 차이 B-A | B/A-1
'26년 매출반영 | 16982490371.5156 | 100% | 16339092620 | 100% | -643397751.5156 | -3.789%
'26년 제조간접원가 | 1262538482.6586 | 7.434% | 977073522.53 | 5.98% | -285464960.1286 | -22.61%
'26년 제조원가 | 15145215296.3441 | 89.18% | 14668117288.6865 | 89.77% | -477098007.6575 | -3.15%
'26년 매출총이익 | 1837275075.1716 | 10.82% | 1670975331.3135 | 10.23% | -166299743.8581 | -9.051%
'26년 판관비( C) | 2275653709.7831 | 13.4% | 2189438411.08 | 13.4% | -86215298.7031 | -3.789%
'26년 영업이익( D) | -438378634.6115 | -2.581% | -518463079.7665 | -3.173% | -80084445.155 | 18.27%
손익분기 판관비 부담 (C+D, 영업이익 < 0) | 1837275075.1716 |  | 1670975331.3135 |  | -166299743.8581
'26년 증분이익 | 3099813557.8302 |  | 2648048853.8435 |  | -451764703.9867
■ 수주완료/확정 ■ 수주 기대 ■ 입찰 경쟁 ■ 투자 미정

## 장표_Item (hidden)
플랜트대기파트 PJT 실행예산 보고 (~4Q 주요 프로젝트)
(단위 : 원/VAT별도)
구분 | BHI 대만 튱샤오 HRSG SCR PKG |  |  | KCL 삼척 화재센터 집진시설 개선 |  | 에코프로INNO HU LHM8K IPPC |  | 도레이 구미 CK3 환경설비 |  | BHI 포스코(포항) LNG복합 |  | 유한화학(화성) RTO 신규 |  | 삼천포발전본부 SCR 개선 |  | 한국소방산업기술원 환경설비 |  | 한주(울산)_SCR |  | 동서발전 음성 복합발전
계약예정일 |  | 26년 3월 |  | 26년 2월 |  | 26년 2월 |  | 26년 3월 |  | 26년 3월 |  | 26년 3월 |  | 26년 3월 |  | 26년 7월 |  | 26년 3월 |  | 26년 9월
계약예정금액 |  | 23800000000 | 100% | 4000000000 | 100% | 374550000 | 100% | 3260000000 | 100% | 6900000000 | 100% | 5300000000 | 100% | 2460000000 | 100% | 1629000000 | 100% | 3000000000 | 100% | 8000000000 | 100%
기계 |  | 3300000000 | 13.87% | 1020000000 | 25.5% | 140669100 | 37.56% | 1710000000 | 52.45% | 2200000000 | 31.88% | 3160000000 | 59.62% | 1520000000 | 61.79% | 874000000 | 53.65% | 1900000000 | 63.33% | 2300000000 | 28.75%
Catalyst Support and Sealing Material
Ammonia Injection Grid with Support
Piping Work
Ammonia Air Mixer
Ammonia Injection Nozzle
전기 |  | 110000000 | 0.4622% | 214000000 | 5.35% | 49995000 | 13.35% | 387000000 | 11.87% | 380000000 | 5.507% |  | 0% | 220000000 | 8.943% | 218000000 | 13.38% | 220000000 | 7.333% | 410000000 | 5.125%
Instrument Cabinet
Relevant Logic & Loop for DCS Control
Junction Box
Local Operating Panel for Dilution Air Blower
Field Work & Material on AFCU Skid
Junction Box on AFCU Skid
PDP
PLC Control Panel
계장 |  | 350000000 | 1.471% |  | 0% |  | 0% |  | 0% | 310000000 | 4.493% |  | 0% |  | 0% |  | 0% |  | 0% | 320000000 | 4%
Flow Control Valve
Flow Transmitter
Flow Transmitter(Vortex)
ON/OFF Valve
Temperature Indicator(With Well)
Temperature Transmitter(With Well)
Manometer
Orifice Plate
Orfice Assembly
Pressure Indicator
Pressure Transmitter
Ammonia Detector Incl. Horn & Beacon
배관 |  |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% | 195000000 | 3.679% |  | 0% |  | 0% |  | 0% |  | 0%
회전기기 | Dilution Air Blower | 320000000 | 1.345% | 170000000 | 4.25% |  | 0% | 145000000 | 4.448% | 120000000 | 1.739% | 320000000 | 6.038% |  | 0% | 94000000 | 5.77% |  | 0% | 150000000 | 1.875%
Ammonia Supply Pump
Sump Pump
Unloading Pump
열교환기 |  |  | 0% | 649000000 | 16.23% |  | 0% |  | 0% |  | 0% | 240000000 | 4.528% |  | 0% |  | 0% |  | 0% |  | 0%
촉매 |  | 14000000000 | 58.82% |  | 0% |  | 0% | 67000000 | 2.055% | 2000000000 | 28.99% |  | 0% |  | 0% |  | 0% |  | 0% | 2550000000 | 31.87%
분석기 |  | 1900000000 | 7.983% |  | 0% |  | 0% | 140000000 | 4.294% | 440100000 | 6.378% |  | 0% |  | 0% |  | 0% |  | 0% | 360000000 | 4.5%
NOx Analyzer for SCR Inlet
NOx & O2 Analyzer for SCR Outlet
NOx Analyzer for SCR Outlet
NH3 Analyzer for SCR Outlet
Local Shelter for Analyzedr
Air conditioner for Analyzer Panel
버너 |  |  | 0% |  | 0% |  | 0% | 23000000 | 0.7055% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0%
Filter |  |  | 0% | 550000000 | 13.75% | 52800000 | 14.1% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0%
활성탄 |  |  | 0% | 250000000 | 6.25% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% | 19200000 | 1.179% |  | 0% |  | 0%
방음룸 |  |  | 0% | 120000000 | 3% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0%
안전관리비 |  |  | 0% | 30000000 | 0.75% |  | 0% | 32000000 | 0.9816% |  | 0% | 40000000 | 0.7547% | 45000000 | 1.829% |  | 0% | 55000000 | 1.833% |  | 0%
외주용역 |  | 470000000 | 1.975% |  | 0% |  | 0% | 20000000 | 0.6135% | 300000000 | 4.348% | 125000000 | 2.358% | 71000000 | 2.886% | 20000000 | 1.228% | 80000000 | 2.667% | 280000000 | 3.5%
Structural analysis
Mechanical detail drawings
3D-Modeling & Piping drawings
Physical Model Flow Test(With CFD)
Document Fee
Electrical & Control
Performance Test
기타 |  | 969900000 | 4.075% | 105000000 | 2.625% | 60756000 | 16.22% | 82360000 | 2.526% | 160900000 | 2.332% | 275000000 | 5.189% | 26500000 | 1.077% | 98000000 | 6.016% |  | 0% | 180000000 | 2.25%
출장 경비(숙식,유류대 포함)
접대비 및 회식비
운반비
보험료
예비비
간접비 |  | 1309000000 | 5.5% | 220000000 | 5.5% | 20600250 | 5.5% | 179300000 | 5.5% | 379500000 | 5.5% | 291500000 | 5.5% | 135300000 | 5.5% | 89595000 | 5.5% | 165000000 | 5.5% | 440000000 | 5.5%
직접원가 |  | 22728900000 | 95.5% | 3328000000 | 83.2% | 324820350 | 86.72% | 2785660000 | 85.45% | 6290500000 | 91.17% | 4646500000 | 87.67% | 2017800000 | 61.9% | 1412795000 | 86.73% | 2420000000 | 80.67% | 6990000000 | 87.38%
판관비 |  | 2927400000 | 12.3% | 492000000 | 12.3% | 46069650 | 12.3% | 400980000 | 12.3% | 848700000 | 12.3% | 651900000 | 12.3% | 302580000 | 12.3% | 200367000 | 12.3% | 369000000 | 12.3% | 984000000 | 12.3%
영업이익 |  | -1856300000 | -7.8% | 180000000 | 4.5% | 3660000 | 0.9772% | 73360000 | 2.25% | -239200000 | -3.467% | 1600000 | 0.03019% | 139620000 | 5.676% | 15838000 | 0.9723% | 211000000 | 7.033% | 26000000 | 0.325%
NOTE.
: 발주 금액 적용

## 장표_Weight (hidden)
플랜트대기파트 PJT 실행예산 보고 (~4Q 주요 프로젝트)
(단위 : 원/VAT별도)
| 구분 | BHI 대만 튱샤오 HRSG SCR PKG | [5 empty] | KCL 삼척 화재센터 집진시설 개선 |  | 에코프로INNO HU LHM8K IPPC |  | 도레이 구미 CK3 환경설비 |  | BHI 포스코(포항) LNG복합 |  | 유한화학(화성) RTO 신규 |  | 삼천포발전본부 SCR 개선 |  | 한국소방산업기술원 환경설비 |  | 한주(울산)_SCR |  | 동서발전 음성 복합발전
| 계약예정일 | 26년 3월 | [5 empty] | 26년 2월 |  | 26년 2월 |  | 26년 3월 |  | 26년 3월 |  | 26년 3월 |  | 26년 3월 |  | 26년 7월 |  | 26년 3월 |  | 26년 9월
| 계약예정금액 |  |  |  |  | 23800000000 | 100% | 4000000000 | 100% | 374550000 | 100% | 3260000000 | 100% | 6900000000 | 100% | 5300000000 | 100% | 2460000000 | 100% | 1629000000 | 100% | 3000000000 | 100% | 8000000000 | 100%
| 구분 | 항목 | Description | Material | Weight(Kg)
| 기계 |  |  |  |  | 3300000000 | 13.87% | 1020000000 | 25.5% | 140669100 | 37.56% | 1710000000 | 52.45% | 2200000000 | 31.88% | 3160000000 | 59.62% | 1520000000 | 61.79% | 874000000 | 53.65% | 1900000000 | 63.33% | 2300000000 | 28.75%
Catalyst Support and Sealing Material
|  |  | H400x200x8x13 | A36 | 38808
|  |  | H300x150x6.5x9 | A36 | 792
|  |  | H200x100x5.5x8 | A36 | 3512.4
|  |  | H125x125x6.5x9 | A36 | 505.8
|  |  | PLATE-12t | A283-C | 1251.6
|  |  | PLATE-9t | A283-C | 90
|  |  | PLATE-3t | A240-304 | 3500
|  |  | M10 B/N/W | A913-B7/A194-2H | 1식
|  |  | M12 B/N/W | A913-B7/A194-2H | 1식
|  |  | M20 B/N/W | A913-B7/A194-2H | 1식
Ammonia Injection Grid with Support
|  |  | 14" PIPE x SCH 40 | A312-TP304 | 525
|  |  | 5" PIPE x SCH 40S | A312-TP304 | 975
|  |  | 4" PIPE x SCH 80S | A312-TP304 | 7500
|  |  | 4" PIPE x SCH 40S | A312-TP304 | 51000
|  |  | 1/2" PIPE x SCH 40S | A312-TP304 | 9750
|  |  | 4" TEE x SCH 40S | A312-TP304 | 750
|  |  | #150 14" FLANGE SO.RF | A105 | 270
|  |  | L-50x50x4 | A276-304 | 9900
Piping Work
|  |  | BOSS, CL.3000, ASTM A105, SW | 300X25A | 20
|  |  | ELBOW 45 DEG LR, WELDED, ASTM A234 WPB, BW, S-STD | 300A | 5
|  |  | ELBOW 90 DEG LR, WELDED, ASTM A234-WPB, BW, S-STD | 300A | 70
|  |  | ELBOW 90 DEG, CL.3000, ASTM A105, SW | 25A | 5
|  |  | FLANGE SO, CL.150, ASTM A105, RF | 300A | 50
|  |  | GASKET SP/WND, CL.150, 316SS WITH GRAPHITE FILLER, INNER & OUTER TING 316SS, RF, 4.5mm TH'K | 300A | 50
|  |  | PIPE, SMLS, ASTM A53-B, PE, S-80 | 25A | 60
|  |  | PIPE, WELDED, ASTM A53-B, BE, S-STD | 300A | 230
|  |  | SOCKOLET, CL.3000, ASTM A105, SW | 300X25A | 20
|  |  | TEE EQUAL, WELDED, ASTM A234-WPB, BW, S-STD | 300A | 5
|  |  | BOSS, CL.3000, ASTM A182-F316, SW | 300X25A | 20
|  |  | FLANGE A182-F316, CL.150, SO, RF | 100 | 200
|  |  | CAP, CL.3000, ASTM A182-F316, FNPT | 25 | 20
|  |  | CAP, WELDED(EFW), ASTM A403-WP316 or A240-316, BW, S-10S | 100 | 100
|  |  | ELBOW 45 DEG LR, WELDED(EFW), ASTM A403-WP316 or A240-316, BW, S-10S | 100 | 40
|  |  | ELBOW 90 DEG LR, WELDED(EFW), ASTM A403-WP316 or A240-316, BW, S-10S | 100 | 375
|  |  | ELBOW 90 DEG LR, WELDED(EFW), ASTM A403-WP316 or A240-316, BW, S-10S | 300 | 15
|  |  | ELBOW 90 DEG, CL.3000, ASTM A182-F316, SW | 25 | 20
|  |  | GASKET SP/WND, CL.150, 316SS WITH GRAPHITE FILLER, INNER & OUTER TING 316SS, RF, 4.5mm TH'K | 100 | 200
|  |  | NIPPLE ; ASME B36.19M ; SMLS ; ASTM A312-TP316 ; TOE ; L=150MM ; | 25 | 30
|  |  | NIPPLE, SMLS, ASTM A312-TP316, PBE ; L=100MM, S-40S | 25 | 30
|  |  | NIPPLE, SMLS, ASTM A312-TP316, PE x TOE ; L=75MM, S-40S | 25 | 40
|  |  | PIPE, SMLS or WELDED, ASTM A312-TP316, PE, S-40S | 25 | 30
|  |  | PIPE, WELDED(EFW), ASTM A312-TP316 or A240-316, BE, S-10S | 100 | 1280
|  |  | PIPE, WELDED(EFW), ASTM A312-TP316 or A240-316, BE, S-10S | 300 | 240
|  |  | SOCKOLET, CL.3000, ASTM A182-F316, SW | 100X25 | 100
|  |  | SOCKOLET, CL.3000, ASTM A182-F316, SW | 300X25 | 20
|  |  | STUD BOLT, A193 GR.B8M CL.2, HEAVY HEX NUT, A194 GR.8M | U5/8-100 | 1600
|  |  | TEE EQUAL, WELDED(EFW), ASTM A403-WP316 or A240-316, BW, S-10S | 100 | 150
|  |  | BOSS, CL.3000, ASTM A105, SW | 100X25 | 200
|  |  | COUPLING FULL, CL.3000, ASTM A105, SW | 25 | 30
|  |  | ELBOW 45 DEG, CL.3000, ASTM A105, SW | 25 | 10
|  |  | ELBOW 90 DEG, CL.3000, ASTM A105, SW | 25 | 40
|  |  | STUD BOLT, SA193 GR.B7 (H.D GALV.), HEAVY HEX NUT, SA194 GR.2H (H.D GALV.) | U7/8-130 | 600
|  |  | SWAGE ECC, SMLS, ASTM A105, BLExPSE, S-40 x S-80 | 100X25 | 20
|  |  | TEE EQUAL, CL.3000, ASTM A105, SW | 25 | 30
|  |  | ELBOW 90 DEG, CL.3000, ASTM A105, SW | 25 | 15
|  |  | COUPLING FULL, CL.3000, ASTM A182-F316, SW | 15 | 25
|  |  | ELBOW 45 DEG, CL.3000, ASTM A182-F316, SW | 15 | 25
|  |  | ELBOW 45 DEG, CL.3000, ASTM A182-F316, SW | 25 | 30
|  |  | ELBOW 90 DEG, CL.3000, ASTM A182-F316, SW | 15 | 135
|  |  | ELBOW 90 DEG, CL.3000, ASTM A182-F316, SW | 25 | 125
|  |  | ELBOW 90 DEG, CL.3000, ASTM A182-F316, SW | 40 | 80
|  |  | ELBOW 45 DEG, CL.3000, ASTM A182-F316, SW | 40 | 40
|  |  | PIPE, SMLS, ASTM A312-TP304, PE, S-40S | 40 | 110
|  |  | NIPPLE, SMLS, ASTM A312-TP316, PBE ; L=100MM, S-40S | 15 | 25
|  |  | PIPE, SMLS, ASTM A312-TP316, PE, S-40S | 15 | 620
|  |  | PIPE, SMLS, ASTM A312-TP316, PE, S-40S | 25 | 365
|  |  | PIPE, SMLS, ASTM A312-TP316, PE, S-40S | 40 | 445
|  |  | SWAGE ECC, SMLS, ASTM A182-F316, PBE, S-40S | 40X15 | 50
|  |  | TEE EQUAL, CL.3000, ASTM A182-F316, SW | 15 | 50
|  |  | TEE REDUCING, CL.3000, ASTM A182-F316, SW | 40X25 | 20
|  |  | CAP, CL.3000, ASTM A182-F316, FNPT | 25 | 100
|  |  | NIPPLE, SMLS, ASTM A312-TP316, PE x NPT ; L=100MM, S-40S | 25 | 100
|  |  | CAP, CL.3000, ASTM A182-F316, FNPT | 15 | 40
|  |  | CAP, CL.3000, ASTM A182-F316, SW | 15 | 20
|  |  | COUPLING FULL, CL.3000, ASTM A182-F316, SW | 15 | 20
|  |  | ELBOW 45 DEG, CL.3000, ASTM A182-F316, SW | 15 | 30
|  |  | ELBOW 90 DEG, CL.3000, ASTM A182-F316, SW | 15 | 120
|  |  | NIPPLE, SMLS, ASTM A312-TP316, PBE, L=75MM, S-40S | 15 | 15
|  |  | NIPPLE, SMLS, ASTM A312-TP316, PE x TOE ; L=100MM, S-40S | 15 | 30
|  |  | PIPE, SMLS, ASTM A312-TP316, PE, S-40S | 15 | 160
|  |  | TEE EQUAL, CL.3000, ASTM A182-F316, SW | 15 | 80
|  |  | TEE REDUCING, CL.3000, ASTM A182-F316, SW | 40X15 | 50
|  | Ammonia Air Mixer | PLATE-6t (I.D 0.5m x 1.0m) | A240-316 | 2000
|  | Ammonia Injection Nozzle | Ammonia Consumption : 90kg/hr (100 wt% of Ammonia) | A312-TP316 | 5EA
Liquid Pressure : 2.5~3.5 bar.g
Air Pressure : 3 bar.g
Air Consumption : By Vendor
Spraying Degree : 55°
| 전기 |  |  |  |  | 110000000 | 0.4622% | 214000000 | 5.35% | 49995000 | 13.35% | 387000000 | 11.87% | 380000000 | 5.507% |  | 0% | 220000000 | 8.943% | 218000000 | 13.38% | 220000000 | 7.333% | 410000000 | 5.125%
Instrument Cabinet
Relevant Logic & Loop for DCS Control
Junction Box
Local Operating Panel for Dilution Air Blower
Field Work & Material on AFCU Skid
Junction Box on AFCU Skid
PDP
PLC Control Panel
|  | SIGNAL CABLE | TC-ER CABLE(TA)(#16×1PR AM) (0.6/1kV TFR-CVV I/C AMS 1.5sq x 1P) |  | 510M
|  | SIGNAL CABLE | TC-ER CABLE(TA)(#16×2PR AM) (0.6/1kV TFR-CVV I/C AMS 1.5sq x 2P) |  | 220M
|  | SIGNAL CABLE | TC-ER CABLE(TA)(#16×3PR AM) (0.6/1kV TFR-CVV I/C AMS 1.5sq x 3P) |  | 550M
|  | SIGNAL CABLE | TC-ER CABLE(TA)(#16×1T AM) (0.6/1kV TFR-CVV I/C AMS 1.5sq x 1T) |  | 190M
|  | CONTROL CABLE | TC-ER CABLE(TA)(#14×1PR AM) (0.6/1kV TFR-CVV AMS 2.5sq x 1P) |  | 500M
|  | CONDUIT PIPE | #22 PF(M) HDG |  | 540M
|  | CABLE GLAND | 1/2"NPT(M) Brass+Ni Plated Ex d Ⅱc |  | 25EA
|  | CABLE GLAND | 3/4"NPT(M) Brass+Ni Plated Ex d Ⅱc |  | 45EA
|  | FLEXIBLE CONDUIT | 1/2""PF(MxM) / 750L Ex d Ⅱc |  | 25EA
|  | FLEXIBLE CONDUIT | 3/4""PF(MxM) / 750L Ex d Ⅱc |  | 45EA
|  | JUNCTION BOX W/SUPPORT(80-P) | SUS316, Ex eb IIC T6 Gb, FOR DIGITAL SIGNAL |  | 1EA
|  | JUNCTION BOX W/SUPPORT(60-P) | SUS316, Ex eb IIC T6 Gb, FOR ANALOG SIGNAL |  | 1EA
|  | LSB w/SUPPORT |  |  | 2EA
|  | PIPE STANCHION W/ BASE PLATE | 2"X1500L 304SS |  | 15EA
|  | INSTRUMENT CABINET | 304SS. OUTDOOR, FOR 1-TRANSMITTER |  | 4EA
|  | MALE CONNECTOR | 1/2"NPT(M)x1/2"O.D A479 TYPE316 |  | 42EA
|  | MALE CONNECTOR | 1/2"NPT(M)x3/8"O.D A479 TYPE316 |  | 7EA
|  | MALE CONNECTOR | 1/2"NPT(M)x1/4"O.D A479 TYPE316 |  | 7EA
|  | BULK-HEAD UNION | 1/2"O.D A479 TP316 |  | 10EA
|  | SEAMLESS TUBE | 1/2"O.Dx0.065" A213-TP316 |  | 105M
|  | SEAMLESS TUBE | 3/8"O.Dx0.049" A213-TP316 |  | 60M
|  | 2-VALVE MANIFOLD | 1/2"NPT(F) x 1/2"NPT(F) A276 TP316 |  | 1EA
|  | U- CHANNEL | 41 x 41 x 3000L 2.6t |  | 20EA
|  | CONDUIT 부속품 |  |  | 1LOT
I | 계장 |  |  |  |  | 350000000 | 1.471% |  | 0% |  | 0% |  | 0% | 310000000 | 4.493% |  | 0% |  | 0% |  | 0% |  | 0% | 320000000 | 4%
i |  | FLOW TRANSMITTER | VORTEX | 40A CL150RF | 5
|  | PRESSURE GAGUE | CHAMBER | 40A CL150RF | 5
|  | TEMP TRANSMITTER | RTD TYPE | 40A CL150RF | 5
|  | FLOW ELEMENT | ORIFICE | 300A CL 150RF | 5
|  | FLOW TRANSMITTER | DIFF. PRESSURE | 15A NPT(F) | 5
|  | PRESSURE TRANSMITTER | DIAPHRAGM | 50A CL150RF | 5
|  | TEMP GAUGE | BIMETAL | 40A CL150RF | 5
|  | FLOW ELEMENT | ORIFICE | 100A CL150# | 5
|  | DIFF. PRESSURE GAUGE | BOURDON | 15A NPT(F) | 5
|  | AMMONIA LEAK DETECTOR | DIFUSON | - | 5
|  | Flow Control Valve | 40A | A312-TP-304L | 5
|  | ON/OFF Valve | 40A | A312-TP-304L | 5
|  | Manometer | 15A | A312-TP-304L | 5
| 배관 | [5 empty] | 0% |  | 0% |  | 0% |  | 0% |  | 0% | 195000000 | 3.679% |  | 0% |  | 0% |  | 0% |  | 0%
| 회전기기 | Dilution Air Blower |  |  |  | 320000000 | 1.345% | 170000000 | 4.25% |  | 0% | 145000000 | 4.448% | 120000000 | 1.739% | 320000000 | 6.038% |  | 0% | 94000000 | 5.77% |  | 0% | 150000000 | 1.875%
120Am3/min x 1200mmAq (Centrifugal, Turbo)
|  |  | Casing | A36
|  |  | Impeller/Blade | A36
|  |  | Shaft | S45C
|  |  | Bed | A36
|  | Ammonia Supply Pump | Not applicable
|  | Sump Pump | Not applicable
|  | Unloading Pump | Not applicable
| 열교환기 | [5 empty] | 0% | 649000000 | 16.23% |  | 0% |  | 0% |  | 0% | 240000000 | 4.528% |  | 0% |  | 0% |  | 0% |  | 0%
| 촉매 |  | Multi-Function Catalyst |  | 51.66m³ (Vendor Proposal) | 14000000000 | 58.82% |  | 0% |  | 0% | 67000000 | 2.055% | 2000000000 | 28.99% |  | 0% |  | 0% |  | 0% |  | 0% | 2550000000 | 31.87%
|  | Outlet NOx concentration | Case 1~7,8~15,17~24 : 40 → 3(Max) [Unit : ppm @15% O2, Dry]
Case 7-1,16 : 40 → 8(Max) [Unit : ppm @15% O2, Dry]
|  | Outlet CO concentration | Case 1~6,10~15,19~24 : 30(Max) [Unit : mg/Nm3 @15% O2, Dry]
Case 7~9,16~18 : 1000(Max) [Unit : mg/Nm3 @15% O2, Dry]
|  | Pressure drop (mmAq) (AIG & Catalyst) | ≤ 35 for Case 2
|  | Ammonia slip (%) | ≤ 2 ppm @ 15% O2, Dry
|  | SO2 to SO3 Conversion Rate | < 1%
| 분석기 |  |  |  |  | 1900000000 | 7.983% |  | 0% |  | 0% | 140000000 | 4.294% | 440100000 | 6.378% |  | 0% |  | 0% |  | 0% |  | 0% | 360000000 | 4.5%
NOx Analyzer for SCR Inlet
Measuring Method: Non-dispersive infrared method
Type : General Purpose
Mesuring Components : Nox
Measuring Range: 0 - 50 / 500 ppm Nox
Ambient Temperature: 0 to 40℃
Voltage rating: 100 to 240 V AC
Rated frequency: 50/60 Hz
Dimensions: Vendor Proposal
Gas Connection: 1/4NPT
Display Language: English
Mounting: Rack without slide rail
Sample Flow rate: 0.5 to 1.0 L/min
Sample Temperature: 0 to 50℃
Sample Pressure: 4.9 to 9.8kPa
Sample Dust: 2 µm or less in particle size
NOx Repeatability: ±1% F.S.
NOx Linearity: ±1% F.S.
NOx Zero drift: ±2% F.S./week
NOx Span drift: ±2% F.S./week
Response time: (90% F.S. response): 30 sec. or less
with NOx/NO Converter
NO Analyzer for SCR Outlet
Measuring Method: Non-dispersive infrared method
Type : General Purpose
Mesuring Components : NO
Measuring Range: 0 - 50 / 500 ppm NO
Ambient Temperature: 0 to 40℃
Voltage rating: 100 to 240 V AC
Rated frequency: 50/60 Hz
Dimensions: Vendor Proposal
Gas Connection: 1/4NPT
Display Language: English
Mounting: Rack without slide rail
Sample Flow rate: 0.5 to 1.0 L/min
Sample Temperature: 0 to 50℃
Sample Pressure: 4.9 to 9.8kPa
Sample Dust: 2 µm or less in particle size
NOx Repeatability: ±1% F.S.
NOx Linearity: ±1% F.S.
NOx Zero drift: ±2% F.S./week
NOx Span drift: ±2% F.S./week
Response time: (90% F.S. response): 30 sec. or less
NO2 is measure by calculation. [NO2 = NOx - NO]
NOx Analyzer for SCR Outlet
Measuring Method: Non-dispersive infrared method
Type : General Purpose
Mesuring Components : NOx
Measuring Range: 0 - 50 / 500 ppm NOx
Ambient Temperature: 0 to 40℃
Voltage rating: 100 to 240 V AC
Rated frequency: 50/60 Hz
Dimensions: Vendor Proposal
Gas Connection: 1/4NPT
Display Language: English
Mounting: Rack without slide rail
Sample Flow rate: 0.5 to 1.0 L/min
Sample Temperature: 0 to 50℃
Sample Pressure: 4.9 to 9.8kPa
Sample Dust: 2 µm or less in particle size
NOx Repeatability: ±1% F.S.
NOx Linearity: ±1% F.S.
NOx Zero drift: ±2% F.S./week
NOx Span drift: ±2% F.S./week
Response time: (90% F.S. response): 30 sec. or less
NO2 is measure by calculation. [NO2 = NOx - NO]
NH3 Analyzer for SCR Outlet
Measuring Method : Tunable Diode Laser
Harzadous area : N/A
Installation Type : In-Situ
Measuring Range : NH3 0 - 50 ppm
Max. Gas Temperature : 450℃
Response time : 1~2 sec
Repeatability : +/- 2% reading or +/- 1 ppm NH3, whichever is greater
Linearity : +/- 2% F.S.
Ambient Operation Temp. : -20℃ to 55℃
Protection Classification : IP66
Signal Output : 4 to 20 mA
Power Supply : 24V DC
I/O Interface : Analog with HART+Modbus Ethernet
Process Connection : ANSI CLASS 150-4 RF (Eq.) Alignment Flange, piping: NPT
Cable : 20m
Local Shelter for Analyzedr
Air conditioner for Analyzer Panel
Manufacture : AIRMAJOR
Cooling : 2300W
Heating : 1800W
Material : Galvanized Steel
Power : 220V, 60Hz
| 버너 | [5 empty] | 0% |  | 0% |  | 0% | 23000000 | 0.7055% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0%
| Filter | [5 empty] | 0% | 550000000 | 13.75% | 52800000 | 14.1% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0%
| 활성탄 | [5 empty] | 0% | 250000000 | 6.25% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% | 19200000 | 1.179% |  | 0% |  | 0%
| 방음룸 | [5 empty] | 0% | 120000000 | 3% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0% |  | 0%
| 안전관리비 | [5 empty] | 0% | 30000000 | 0.75% |  | 0% | 32000000 | 0.9816% |  | 0% | 40000000 | 0.7547% | 45000000 | 1.829% |  | 0% | 55000000 | 1.833% |  | 0%
| 외주용역 |  |  |  |  | 470000000 | 1.975% |  | 0% |  | 0% | 20000000 | 0.6135% | 300000000 | 4.348% | 125000000 | 2.358% | 71000000 | 2.886% | 20000000 | 1.228% | 80000000 | 2.667% | 280000000 | 3.5%
|  | Structural analysis | (AIG, CSS, AFCU & Vaporizer Analysis, Foundation Loading Data, Anchor Calculation)
|  | Mechanical detail drawings | (P&ID, GA, Foundation, Catalyst Frame and Gas Sealing, AIG, Equiment Detail Drawing)
|  | 3D-Modeling & Piping drawings | (3D Modeling Works, Piping Arrangement, ISO, Support, Terminal Point List Drawing, B.O.M, Valve List)
|  | Physical Model Flow Test(With CFD) | (Modeling, Data Input & Simulation, Study Report)
|  | Electrical & Control | HRSG_CONDUIT LAYOUT DRAWING FOR SCR SYSTEM
HRSG_CABLE SCHEDULE FOR INSTRUMENTS FOR SCR SYSTEM
HRSG_WIRING DIAGRAMS FOR INSTRUMENTS FOR SCR SYSTEM
HRSG_INSTRUMENT LOCATION DRAWING FOR SCR SYSTEM
HRSG_INSTRUMENT INSTALLATION FOR SCR SYSTEM
HRSG_LOCAL JUNCTION BOX & INSTRUMENT RACK/STANCHION DRAWINGS FOR SCR SYSTEM
HRSG_DCS I/O LIST FOR SCR SYSTEM
HRSG_CONTROL LOGIC & LOOP DIAGRAM FOR SCR SYSTEM
Performance Test
| 기타 |  |  |  |  | 969900000 | 4.075% | 105000000 | 2.625% | 60756000 | 16.22% | 82360000 | 2.526% | 160900000 | 2.332% | 275000000 | 5.189% | 26500000 | 1.077% | 98000000 | 6.016% |  | 0% | 180000000 | 2.25%
출장 경비(숙식,유류대 포함)
접대비 및 회식비
운반비
보험료
예비비
| 간접비 |  |  |  |  | 1309000000 | 5.5% | 220000000 | 5.5% | 20600250 | 5.5% | 179300000 | 5.5% | 379500000 | 5.5% | 291500000 | 5.5% | 135300000 | 5.5% | 89595000 | 5.5% | 165000000 | 5.5% | 440000000 | 5.5%
| 직접원가 |  |  |  |  | 22728900000 | 95.5% | 3328000000 | 83.2% | 324820350 | 86.72% | 2785660000 | 85.45% | 6290500000 | 91.17% | 4646500000 | 87.67% | 2017800000 | 61.9% | 1412795000 | 86.73% | 2420000000 | 80.67% | 6990000000 | 87.38%
| 판관비 |  |  |  |  | 2927400000 | 12.3% | 492000000 | 12.3% | 46069650 | 12.3% | 400980000 | 12.3% | 848700000 | 12.3% | 651900000 | 12.3% | 302580000 | 12.3% | 200367000 | 12.3% | 369000000 | 12.3% | 984000000 | 12.3%
| 영업이익 |  |  |  |  | -1856300000 | -7.8% | 180000000 | 4.5% | 3660000 | 0.9772% | 73360000 | 2.25% | -239200000 | -3.467% | 1600000 | 0.03019% | 139620000 | 5.676% | 15838000 | 0.9723% | 211000000 | 7.033% | 26000000 | 0.325%
NOTE.
: 발주 금액 적용

## BHI (hidden)
플랜트대기파트 1Q PJT 실행예산 보고
■ BHI PJT
프로젝트명 | Amiral |  | Qatar |  | Rabigh |  | Tung siao
수주금액 (수주예상금액) | 2360000000 | 100% | 9150000000 | 100% | 9290000000 | 100% | 24800000000 | 100%
기계 | 1309000000 |  | 3983000000 |  | 3482600000 |  | 4176740000
전,계장 | 434000000 |  | 1260000000 |  | 1583500000 |  | 493920000
촉매 | 380000000 |  | 2608000000 |  | 2369600000 |  | 14250000000
구매품 | 232000000 |  | 719308800 |  | 1320300000 |  | 2435040000
기타 (경비, 보험료 외) | 120640000 |  | 185000000 |  | 134530000 |  | 964300000
직접원가 계 | 2475640000 | 104.9% | 8755308800 | 95.69% | 8890530000 | 95.7% | 22320000000 | 90%
간접비 (A) | 0 | 0% | 393450000 | 4.3% | 399470000 | 4.3% | 1066400000 | 4.3%
판관비 (B) | 266680000 | 11.3% | 0 | 0% | 0 | 0% | 1413600000 | 5.7%
영업이익 (C) | -382320000 | -16.2% | 1241200 | 0.01357% | 5.9605e-08 | 6.416e-16% | 0 | 0%
A + B + C (간+판+영) | -115640000 | -4.9% | 394691200 | 4.314% | 399470000 | 4.3% | 2480000000 | 10%
구매네고 | -42359290 | -1.795% | 578748800 | 0% | (실주) | 0% | (예정) | 0%
최종 간+판+영 | -73280710 | -3.105% | 973440000 | 10.64% | 399470000 | 4.3% | 2480000000 | 10%

## 도레이 (hidden)
플랜트대기파트 1Q PJT 실행예산 보고
■ 도레이 구미 PJT
프로젝트명 | CK-1 |  | CK-2 |  | CK-3
수주금액 (수주예상금액) | 1697000000 | 100% | 2140000000 | 100% | 2950000000 | 100%
기계 | 904000000 |  | 1090000000 |  | 1692000000
전,계장 | 125000000 |  | 247000000 |  | 387000000
촉매 | 41000000 |  | 70000000 |  | 51300000
구매품 | 302000000 |  | 336000000 |  | 267750000
기타 (경비, 보험료 외) | 20000000 |  | 10000000 |  | 85000000
직접원가 계 | 1392000000 | 82.03% | 1753000000 | 81.92% | 2483050000 | 84.17%
간접비 (A) | 0 | 0% | 0 | 0% | 126850000 | 4.3%
판관비 (B) | 0 | 0% | 0 | 0% | 262550000 | 8.9%
영업이익 (C) | 305000000 | 17.97% | 387000000 | 18.08% | 77550000 | 2.629%
A + B + C (간+판+영) | 305000000 | 17.97% | 387000000 | 18.08% | 466950000 | 15.83%
구매네고 | - | 0% | - | 0% | - | 0%
최종 간+판+영 | 305000000 | 17.97% | 387000000 | 18.08% | 466950000 | 15.83%

## KTC (hidden)
플랜트대기파트 1Q PJT 실행예산 보고
■ 밧데리 화재시험 PJT
프로젝트명 | KTC (오창) |  | KCL (삼척)
수주금액 (수주예상금액) | 5520000000 | 100% | 4000000000 | 100%
기계 | 3062000000 |  | 1665000000
전,계장 | 550000000 |  | 270000000
구매품 | 964340000 |  | 1204400000
기타 (경비, 보험료 외) | 213700000 |  | 140000000
직접원가 계 | 4790040000 | 86.78% | 3279400000 | 81.98%
간접비 (A) | 237360000 | 4.3% | 172000000 | 4.3%
판관비 (B) | 491280000 | 8.9% | 356000000 | 8.9%
영업이익 (C) | 1320000 | 0.02391% | 192600000 | 4.815%
A + B + C (간+판+영) | 729960000 | 13.22% | 720600000 | 18.02%
구매네고 | 0 | 0% | (예정) | 0%
최종 간+판+영 | 729960000 | 13.22% | 720600000 | 18.02%

## 실행예산서 (2) (hidden)
■ 실행예산서 | #REF! | [7 empty] | 비용 사용계획
항목 | 업체명 | 계정명 | 최초 실행원가 (2025.02) A | 네고 반영가 C | 증감 (C-A) | 비고 |  | 합계 | 전년누계(~2023) | 1월 | 2월 | 3월 | 4월 | 5월 | 6월 | 7월 | 8월 | 9월 | 10월 | 11월 | 12월 | 1월 ~
외주가공비-설비(도급) |  |  | 11829500000 | 11238025000 | -591475000 |  |  | 0
Bag Filter | 해밀 | 외주가공비-설비(도급) | 2060000000 | 1957000000 | -103000000 | Filter Bag 포함, 설치 공사 제외 | 네고 반영율 | 0
송풍기 | 동아풍력 | 외주가공비-설비(도급) | 952000000 | 904400000 | -47600000 |  | 0.95 | 0
열교환기 | 에어로피에치이 | 외주가공비-설비(도급) | 1780000000 | 1691000000 | -89000000 | 공냉식, 수냉식 열교환기 각 2단 구성
냉각탑 | 범양냉동공조 | 외주가공비-설비(도급) | 156000000 | 148200000 | -7800000 | 냉각탑 인버터 제외(전계장에 인버터 포함)
약품펌프, 순환펌프 | 플러스펌프모터 | 외주가공비-설비(도급) | 271800000 | 258210000 | -13590000
AC Tower, Cyclone, Duct | 이에프솔루션 | 외주가공비-설비(도급) | 3906000000 | 3710700000 | -195300000 | Stack, 배관, 보온 포함, 수동 밸브류 포함
밸브 | 미정 | 외주가공비-설비(도급) | 50000000 | 47500000 | -2500000 | 자동 밸브류
Scrubber | 대성FRP | 외주가공비-설비(도급) | 469100000 | 445645000 | -23455000
Pall Ring, Demister | 조일환경 | 외주가공비-설비(도급) | 32000000 | 30400000 | -1600000
활성탄 | 카본텍 | 외주가공비-설비(도급) | 348000000 | 330600000 | -17400000 | 5,500원/kg 적용
전계장 | 이맥시스템 | 외주가공비-설비(도급) | 1050000000 | 997500000 | -52500000
NaOH 탱크 | 서호플랜트 | 외주가공비-설비(도급) | 14000000 | 13300000 | -700000
AC Tower Slide Gate, Rotary V/V |  | 외주가공비-설비(도급) | 45000000 | 42750000 | -2250000
Compressor |  | 외주가공비-설비(도급) | 50000000 | 47500000 | -2500000
유지보수용 호이스트 |  | 외주가공비-설비(도급) | 40000000 | 38000000 | -2000000 | 1톤 x 4대
모터룸 | 서해플랜트 | 외주가공비-설비(도급) | 234000000 | 222300000 | -11700000
전기실 룸 및 토목공사 |  | 외주가공비-설비(도급) | 350000000 | 332500000 | -17500000
Rupture Disk | 세원T&S | 외주가공비-설비(도급) | 21600000 | 20520000 | -1080000
추후선정 |  |  | 0 | 0 | 0 |  |  | 0
|  | 외주가공비-설비(도급) |  | 0 | 0 |  |  | 0
|  | 외주가공비-설비(도급) |  | 0 | 0 |  |  | 0
|  | 외주가공비-설비(도급) |  | 0 | 0 |  |  | 0
|  | 외주가공비-설비(도급) |  | 0 | 0 |  |  | 0
|  | 외주가공비-설비(도급) |  | 0 | 0 |  |  | 0
|  | 외주가공비-설비(도급) |  | 0 | 0 |  |  | 0
|  | 외주가공비-설비(도급) |  | 0 | 0 |  |  | 0
|  | 외주가공비-설비(도급) |  | 0 | 0 |  |  | 0
|  | 외주용역비-도급 |  | 0 | 0 |  |  | 0
|  | 외주용역비-도급 |  | 0 | 0 | EG,OS,SM |  | 0
|  | 지급임차료-기타 |  | 0 | 0 |  |  | 0
|  | 외주가공비-설비(도급) |  | 0 | 0 | 부족분은 예비비 사용 (23,557,220) |  | 0
추가 증액 | [7 empty] | 0
|  | 외주가공비-설비(도급) |  | 0 | 0 |  |  | 0
|  | 외주가공비-설비(도급) |  | 0 | 0 |  |  | 0
|  | 외주가공비-설비(도급) |  | 0 | 0 |  |  | 0
|  | 외주가공비-설비(도급) |  | 0 | 0 |  |  | 0
|  | 외주가공비-설비(도급) |  | 0 | 0 |  |  | 0
|  | 외주가공비-설비(도급) |  | 0 | 0 |  |  | 0
|  | 외주가공비-설비(도급) |  | 0 | 0 |  |  | 0
|  | 외주가공비-설비(도급) |  | 0 | 0 |  |  | 0
|  | 외주가공비-설비(도급) |  | 0 | 0 |  |  | 0
|  | 외주용역비-도급 |  | 0 | 0 |  |  | 0
|  | 외주가공비-설비(도급) |  | 0 | 0 |  |  | 0
|  |  |  | 0 | 0 |  |  | 0
안전관리비 |  |  | 346000000 | 346000000 | 0 |  |  | 0
안전관리자 |  | 외주용역비-도급 | 36000000 | 36000000 | 0 | 1인 4개월 |  | 0
산업안전보건관리비 |  | 소모품비-안전용품 | 310000000 | 310000000 | 0 | 안전용품 포함
안전용품 |  | 소모품비-안전용품 |  | 0 | 0 | 요율 적용 |  | 0
경비 |  |  | 115000000 | 115000000 | 0 |  |  | 0
엔지니어링 비용 |  | 외주용역비-도급 | 60000000 | 60000000 | 0 |  |  | 0
여비교통비 |  | 여비교통비-국내 | 55000000 | 55000000 | 0 | 3명 4개월, 컨테이너 포함 |  | 0
|  | 차량유지비-수선비_법인차량 |  | 0 | 0 |  |  | 0
|  | 차량유지비-기타_법인차량 |  | 0 | 0 |  |  | 0
|  | 소모품비-기타 |  | 0 | 0 |  |  | 0
|  | 운반비-국내 |  | 0 | 0 |  |  | 0
|  | 사택관리비 |  | 0 | 0 |  |  | 0
|  | 세금과공과-등록면허세 |  | 0 | 0 |  |  | 0
|  | 복리후생비-업무추진비 |  | 0 | 0 |  |  | 0
|  | 지급임차료-지게차 |  | 0 | 0 |  |  | 0
|  | 지급임차료-기타 |  | 0 | 0 |  |  | 0
|  | 지급수수료-기타 |  | 0 | 0 |  |  | 0
|  | 지급수수료-기타 |  | 0 | 0 |  |  | 0
보험료-보증 |  |  | 60000000 | 60000000 | 0 |  |  | 0
계약이행 및 하자증권 |  | 보험료-보증 | 30000000 | 30000000 | 0 |  |  | 0
하도급대금지급보증수수료 |  | 보험료-보증 | 10000000 | 10000000 | 0 |  |  | 0
건설기계대여대금 지급보증 |  | 보험료-보증 | 20000000 | 20000000 | 0 |  |  | 0
예비비 |  |  | 120000000 | 60000000 | 0 | 100억 이상공사 0.8% 이하 기준 적용 |  | 0
예비비 |  | 예비비 | 60000000 | 60000000 | 0 |  |  | 0
돌관작업비 |  | 예비비 | 60000000 | 60000000 | 0
직접원가 합계 |  |  | 12470500000 | 11819025000 | -591475000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
제조간접비 |  |  | #REF! | #REF! | #REF!
관리자 급여 외 | #REF! | 제조간접비 | #REF! | #REF! | #REF! |  |  | 0
합계 |  |  | #REF! | #REF! | #REF! | 0

## 제안서용 견적 (hidden)
| 설비명 |  |  |  |  | 제출가 | 비고
1 | System Duct | 668480000 |  |  | 668480000 | 690000000 |  |  | 이에프솔루션 | 3955034000 | (자동밸브 포함) | 해밀 | 수량 | 총 금액 | 단가
2 | Dust Chamber | 723200000 |  |  | 723200000 | 740000000 |  |  | 백필터 | 2060000000 |  | PE | 2304 | 52992000 | 23000
3 | Heat Exchanger | 1780000000 |  |  | 1780000000 | 1800000000 |  |  | 동아풍력 | 952000000 |  | PTFE | 4032 | 282240000 | 70000
4 | Cooling Fan | 200000000 |  |  | 200000000 | 200000000 |  |  | 에어로피에치이 | 1780000000
5 | Cooling Tower | 156000000 |  |  | 156000000 | 165000000 |  |  | 플러스모터펌프 | 285800000 | (NaOH Tank 포함) | 마이크로원
6 | Supply Pump | 136560000 |  |  | 136560000 | 145000000 |  |  | 스크러버 | 469100000 |  | Glass Fiber | 4056 | 154128000 | 38000
7 | Bag Filter System | 2060000000 | 21600000 |  | 2081600000 | 2150000000 | 파열판 |  | 냉각탑 | 156000000 |  | PTFE | 4056 | 239304000 | 59000
8 | Main Fan | 376000000 |  |  | 376000000 | 393000000 |  |  | 이맥 | 1050000000
9 | A/C Tower | 883200000 | 348000000 | 45000000 | 1276200000 | 1350000000 | 활성탄, 슬라이드 게이트
10 | Wet Scrubber | 469100000 | 32000000 |  | 501100000 | 540000000 | 폴링, 데미스터
11 | Scrubber Fan | 376000000 |  |  | 376000000 | 393000000
12 | Spray Pump | 82440000 |  |  | 82440000 | 90000000
13 | Chemical Pump | 66800000 |  |  | 66800000 | 75000000
14 | 수동 Valve | 150000000 |  |  | 150000000 | 150000000
14 | 자동 Valve | 50000000 |  |  | 50000000 | 50000000
15 | Stack | 362200000 |  |  | 362200000 | 395000000
16 | 기계 설치공사 | 1067954000 | 234000000 |  | 1301954000 | 1380000000 | 모터룸 | 797995000
17 | 전계장 | 1050000000 | 350000000 |  | 1400000000 | 1640000000 | 전기실 및 토목 | 435270000
18 | 운송비 및 장비비 | 50000000 |  |  | 50000000 | 60000000
19 | 기타 | 865000000 |  |  | 865000000 | 870000000 | (호이스트, 컴프레서, 안전관리비, 엔지니어링비, 시운전, 안전관리자. 보험료, 여비교통비)
20 | 일반관리비 및 이윤 | 825000000 |  |  | 825000000 | 1233000000
| 합계 | 12397934000 |  |  | 13428534000 | 14509000000
|  | 호이스트 | 40000000
|  | 컴프레서 | 50000000
|  | 안전관리비 | 308000000
|  | 엔지니어링비 | 60000000
|  | 안전관리자 | 36000000
|  | 시운전비 | 6000000
|  | 여비교통비 | 55000000
|  | 보험료 | 60000000
|  | 예비비 | 250000000
865000000